## Pandalur -covering
R.DINESH KUMAR ASS.ENGINEER
RC NO:- 1/AE/Nilgiris/Pandalur/BILL Dt:
TO,
EXE.ENGINEER
TNCSC
GOPALAPURAM
CHENNAI
Sir,
Sub: | TNCSC –Coimbatore Sub Division - Nilgiris Region – Construction of New Taluk operational godown of 2500M.T (1X1500MT, 1X1000MT) capacity in TNCSC campus at Survey No.2347/1 to an extent of 1.21.44 Hectare at Nelliyalam Village in Pandalur Taluk in Nilgiris District. - L.S III & Part Bill – Submitted Reg
Ref: LS / Agt.No. 362 /2023-24
I submit here with the L.S I & Part Bill for the following work for favour of taking further necessary action please. |  |  |  |  | CONSTRUCTION OF NEW TALUK OPERATIONAL GODOWN OF 2500M.T (1X1500MT, 1X1000MT) CAPACITY IN TNCSC CAMPUS AT SURVEY NO.2347/1 TO AN EXTENT OF 1.21.44 HECTARE AT NELLIYALAM VILLAGE IN PANDALUR TALUK IN NILGIRIS DISTRICT.
S.No | Name of work
1 | Construction of New Taluk operational godown of 2500M.T (1X1500MT, 1X1000MT) capacity in TNCSC campus at Survey No.2347/1 to an extent of 1.21.44 Hectare at Nelliyalam Village in Pandalur Taluk in Nilgiris District.
Thanking you
Encl: Bill form with M.Book |  |  |  | Yours Faithfully
6981ACE, 6979ACE, 58266CE |  |  | For Tamil Nadu Civil Supply Corporation
Asst.Engineer
TNCSC Coimbatore
Kindly forwarding the bill for payment to Executive Engineer / Chennai
Counter Signed
JR/Senior Regional Manager
TNCSC Nilgiris

## BOQ
Construction of New Taluk operational godown of 2500M.T capacity in TNCSC campus at Survey No.2347/1 to an extent of 1.21.44 Hectare at Nelliyalam Village in Pandalur Taluk in Nilgiris District.
BOQ
S.No | Item Description | Quantity | Units | Rate | Amount
1.01 | Clearing Scrub Jungle as directed by the departmental officers. | 4000 | M2 | 7.55 | 30200
1.02 | EARTH WORK excavation for foundation in all classes of soils and subsoils to full depth, as may be directed except in hard rock, requiring blasting including initial leads and lifts and refilling the sides of foundation with excavated earth in 150mm layers well watered rammed and consolidated including depositing surplus earth with in the Godown or inside compound in places shown with initial leads and lifts, clearing, leveling site, shoring, strutting, baling of water wherever necessary etc., complete complying with standard specification and as directed. | 447 | M3 | 279.85 | 125092.95
1.03 | Refilling with excavated earth in basement including watering, rammed and consolidated etc., complete complying with standard specifications and as directed. | 273 | M3 | 54.55 | 14892.15
1.04 | Supplying and filling in foundation with Gravel in layers of not exceeding 150mm thick well watered, rammed and consolidated including watering etc., complete complying with standard specification and as directed. | 450 | M3 | 2347 | 1056150
1.05 | Refilling with conveyed earth to a lead of 10KM for filling in foundation and basement including watering, rammed and consolidated etc., complete and as directed by the departmental officers. | 824 | M3 | 278.3 | 229319.2
1.06 | Supplying and filling in basement with wetmix 250mm thick in layers of not exceeding 250mm thick, well watered, rammed and consolidated including machineries for hire and running charges leader 5 Cum capacity, hire charges for tipper, water sprinkler,` vibratory roller all labour charges etc., complete complying with standard specification and as directed | 300 | M3 | 4269.95 | 1280985
1.07 | CEMENT CONCRETE 1:5:10(one cement , five sand and ten aggregate)using 40mm gauge hard broken granite stone jelly for foundation including de-watering side shuttering , strutting, wherever necessary including curing etc., complete complying with standard specifications and as directed. | 270 | M3 | 8093 | 2185110
1.08 | BRICK WORK in cement mortar 1:5(One cement ,Five sand)using best quality Country Bricks of size 8 ¾”x4 ¼” x2¼’’ for walls including cost of scaffolding curing ,finishing etc., complete complying with standard specifications and as directed. In foundation and basement. | 141 | M3 | 7536.75 | 1062681.75
1.09 | In ground floor Upto 4.50M height above basement. | 243 | M3 | 7647.2 | 1858269.6
1.1 | Above 4.50M height above basement. | 103 | M3 | 7870.19 | 810629.57
1.11 | Providing FORM WORK for centering the soffits of all reinforcement concrete work including strutting to the required (3 metre) height with mild-steel sheets of size 90cmx60cm 10 gauge stiffened with welded mild steel angles of size 25mmx25mmx3mm laid with country wood joist of average of size 10cmx6.50cm at about 90cm centres with casurina props of 13cm dia at 75cm centre to centre with all nails coir,wedges complete and removing the form work after necessary curing period as directed by the corporations officers. The rates should inclusives of cutting , bending, welding , charges of M.S sheets, M.S. angles etc., Complete Column footing, Plinth beam, top tie beame | 715 | M2 | 1159.9 | 829328.5
1.12 | Rectangular beams and floor slabs, tie beams, lintels, landing slab, loft etc., | 805 | M2 | 1278.8 | 1029434
1.13 | Column, ratguard slab, curtain slab and sun shades etc., | 906 | M2 | 1406.65 | 1274424.9
1.14 | Supplying, fabricating and placing in position MS/RTS grills for reinforcement for all R.C.C.works including cost of steel, labour for straightening, bending, cranking, tying grills with 18 gauge galvanized binding wire and placing grills in position complete complying with standard specification and as directed.. | 524.6 | QTL | 10099.75 | 5298328.85
1.15 | Supplying and fixing (under lintel grove) cold rolled ROLLING SHUTTERS of approved quality of 18 gauge 7.5 cm wide cold rolled lathe section in one piece interlocked together with specially designed pipe shaft with adequate number of high tensile steels wire springs of approved quality complete with brackets side guides and arrangements for inside and outside locking arrangements with push and pull operations and pulling back handle with all accessories without workmanship and the entire shutter painted with two coats of best quality anti-corrosive nut brown color paint over one coat of red oxide primer and clear opening of 1.8 M width 2.60 M | 10 | NOS | 14635 | 146350
1.16 | Supplying and fixing of Steel glazed AIR INLET WINDOWs of size 0.6m x 0.6m using extruded angles (Z-section) alround for frame with centre mullion (T-section) and shutter with the same Z-section properly fixed with hinges 2 nos. for each shutter. The panel of shutter fixed with G.I. sheet of'18 gauge and necessary locking arrangements including weld mesh cover using weld mesh 25mm x 25mm x 10mm gauge and welded with iron square bars of 10mm size - 3nos. horizontally and 2nos. vertically welded together to form a grill and welding grill to the main frame with 4mm thick and 12mm wide MS flats. The rate is also inclusive of one coat of steel primer and two coats of ANTI CORROSIVE METALLIC paint and quality, 2 nos. | 36 | NOS | 3453.2 | 124315.2
1.17 | Supplying and fixing steel N-Type VENTILATOR of size 2.60m x 0.60m using extruded angle (Z-section 25mmx25mmx3mm) for outer frames with center mullion (T-section)and with weld mesh of 25mmx25mm 10guage on all three sides ( 2 verticals 1 horizontal) and 10mm size MS square bars horizontally one at top and one at bottom welded to the frames with necessary MS flats of size 20mmx4mm thick | 92 | NOS | 4250 | 391000
1.18 | Providing vacuum de watered controlled cement surfacing 100mm thick in required slope and chamber confirming M20 grade with 20mm size stone aggregate cast in situ ,smooth finish and leveling with double framed screed vibrator ,excess water to be removed through vacuum pump with bottom and top filter mat duly sealing the edges all round including provisions of polythene sheet below the concrete layer before placing of concrete and finishing with paver floated and power trawler to obtain the hard surface including provision of expansion joints at 6mtr intervals across the platform by cutting 6mm wide and full depth of concrete by contractors | 1503 | M2 | 1653.4 | 2485060.2
1.19 | PLASTERING with cement mortor 1:5 (one cement and five sand) 12mm thick including cost of scaffolding, finishing, curing etc., complete complying with standard specification and as directed. | 3522 | M2 | 356.05 | 1254008.1
1.2 | PLASTERING with the exposed RCC surface with C.M.1:3(one cement and three sand) 10mm thick including cost of scaffolding, finishing, curing etc., complete complying with standard Specification and as directed. | 1350 | M2 | 401.1 | 541485
1.21 | Painting the walls with two coats of exterior emulsion paint of first class approved quality and colour over a priming coat including thorough scrapping, clean removal of dirt, and including necessary plaster of paris putty, wherever required etc., complete complying with standard specification and as directed. | 3209 | M2 | 309.2 | 992222.8
1.22 | Supplying, fabricating and fixing in position M.S.Channel 100x50x6mm at the edge of loading platform with M.S bolt of 16mm at the edge of loading platform with M.S bolt of 16mm at the edge of loading platform finishing in flush with the slab with C.M 1:3 complete including painting the exposed surface of MS channel with two coats of ANI Corrosive metalic net brown colour paint over one coat red oxide primer etc., complete. | 76.4 | RM | 1277 | 97562.8
1.23 | Supplying and fixing of Rotary Ventilators over the roof with necessary bolt and nut arrangement to withstand the wind velocity as specified by the departmental officers. (Size 600mm x 600mm) | 11 | NOS | 18000 | 198000
1.24 | Supplying and laying of profiled colour galvalume sheet with combination 55A1:43 4Zn:1:6SI of TCT bent type 0.47mm thick and standard width of 1.06m with yield strength of 550 MPA made from high tensile/ CR sheets of approved quality for roofing with necessary fixing arrangements like 65m abd long hexagonal head screws with EPDM rubber seal etc., complete complying with standard specification and as directed by the departmental officer. (Test certificate for quality should be furnished on receipt of material at site) | 1911 | M2 | 1198.15 | 2289664.65
1.25 | Supplying and roofing with Galvalume sheet ridge pieces of size 1.00M x 0.7M, 0.47mm thick with necessary U or J bolt and nuts G.I washers etc., complete For the above works skilled man power, necessary tools, equipments, power supply, water supply including transport, any other statuary approval required for the transporting the materials shall be duly obtained by the contractor. (Test certificate for quality should be furnished on receipt of material at site) | 107 | RM | 656.5 | 70245.5
1.26 | Supplying and fixing corrugated Poly Carbonate sheet of size 3mx1.06m of 3mm thick on the roof in-between the colour coated Galvalume sheets for proper lighting with necessary G.I screws and EPDM rubber washers, Complying with standard specification and as direct and specified by the departmental officers including cost of loading unloading and transportion charges etc., complete. | 34 | M2 | 1427.85 | 48546.9
1.27 | Painting the walls with two coats of oil bound distemper over one coat of water based cement primer including cost of distemper, primer, cleaning, scrabbing the walls, rendering the walls smooth with necessary putty, brushes, scaffolding arrangements, labour charges etc., complete, complying standard specification and as directed. ( The quality and colour of oil bound distemper should got approved by the Executive Engineer before use.) | 1865 | M2 | 197.75 | 368803.75
1.28 | Supplying and fixing of 40 X 6mm G.I Flat over the galvalume sheet roofing which is placed on the top of Purlin in the longitudinal direction to avoid the lifting of roofing during heavy wind. The rate is inclusive of GI screws 75mm length with rubber and aluminium washer, drilling hole over GI Flat to hold the sheet and purlin with necessary adhesive flashing tap directly over the galvalume sheet including labour charges for fixing, conveyance, loading, unloading and cutting etc. complete as directed by the departmental officers. | 842 | RM | 241.35 | 203216.7
1.29 | Supplying fabricating, hoisting and erection of ROOF TRUSSES PURLINS AND WIND BRACING with structural steel member like angle and channel iron and M.S.plates for all truss, purlin members including all cutting drilling holes, and welding and fixing of member with necessary bolts and nuts, of approved quality and hoisting, aligning and placing the trusses in position etc., complete the trusses will be manufactured as per the detailed plan. The rate should include the cost of painting with one coat of red oxide primer with two coats of best quality of aluminium paint over priming coat. | 35811 | Kg | 145.2 | 5199757.2
1.3 | Reinforcement Cement Concrete 1:1 ½ :3 ( one cement, one and half sand, three aggregate) using 20mm of hard broken granite stone for all RCC works using machine for mixing concrete excluding cost of centering, Strutting, shuttering, and fabrication of reinforcement and placing the grills in position etc., but including finishing and curing etc., complete complying with standard specifications and as directed. In foundation and basement | 154 | M3 | 12500.45 | 1925069.3
1.31 | In ground floor Upto 4.50M height above basement. | 72 | M3 | 12668.25 | 912114
1.32 | Above 4.50M height from basement | 69 | M3 | 12998.75 | 896913.75
1.33 | Supplying and filling in foundation, basement, etc., with filling crushed stone sand in layers of not more than 15cm thick well watered, rammed and consolidated etc., complete complying with standard specification and as directed by the departmental officers. | 16 | M3 | 3455.65 | 55290.4
1.34 | Cement Concrete 1:2:4 ( one cement, two sand, four aggregate) using 20mm of hard broken granite stone for all RCC works using machine for mixing concrete excluding cost of centering, Strutting, shuttering, and fabrication of reinforcement and placing the grills in position etc., but including finishing and curing etc., complete complying with standard specifications and as directed. In foundation basement | 6 | M3 | 11812.25 | 70873.5
1.35 | In ground floor upto 4.50M height above basement | 5 | M3 | 11980 | 59900
1.36 | Supplying and fixing in position of rain beating RCC Jolly, 5 cm thick in cement concrete 1:2:4 using 20mm stone jelly, including cost and conveyance of all materials labour charges for mixing, laying, casting, curing and fixing in position of jolly as directed and cost of mould, fabrication of reinforcement, etc., complete. | 3 | M2 | 1514.45 | 4543.35
1.37 | Supplying and fixing of UPVC ventilator (Up-plasticized poly vinyl choloride) louvered ventilators of form profile size outer frame 60x58 mm and shutter profile size 60 x78mm both profiles reinforced with GI 1mm 125 GSM and 100% corrosion free multi colored chamber section with wall thick of 2mm. The EPDM rubber (Black colour ) covered with all the edges frame shutters. The corners and joints to be welded and cleaned. Radiation pin headed glass 4mm thick should be provided to the louvers. The Ventilator should be fixed to the wall with 100% packing with screws silicon packing round the frames. The Ventilator should got approved from Executive Engineer. | 1.2 | M2 | 8106 | 9727.2
1.38 | Supplying and fixing M.S Grill to special windows and ventilators etc using 20mmx6mm angle including cost of MS grill, one of red oxide and fixing in position etc. complete complying with Standard Specification and as directed. | 100 | KG | 114.95 | 11495
1.39 | Fabricating, supplying and fixing in position of SOLID PVC DOORS with frames of sizes as per the specifications given below: PVC door frames made out of best quality PVC extruded section of 40mm * 58 mm * 2.50 mm +/- 0.3 mm thick, having multi chamber cross section and duly reinforced with steel to be mitre cut at the corners and welded including providing tie rod at the bottom and necessary weather seal etc., and PVC door shutters made out of extruded plastic section of 60 mm * 24 mm size in the configuration of an “A” section for shutter frames and multi-chamber hollow plastic section of 200 mm 200 mm1 mm (average thickness) with tongue and groove section for panels etc., with necessary holdfasts, rubber beedings, furniture fittings, locking | 5 | NOS | 3325 | 16625
1.4 | Supplying and fixing in position Indian Water Closet (Oriya type) of size 580 x 440mm white glazed earthern ware of approved quality and brand with "P" or "S" trap conforming to BIS with sand cushion and forming flooring alround the closet using 40mm broken brick jelly in lime concrete 1:2:5 (One lime, Two sand and Five brick jelly) 100mm thick and finishing the top to the required slope and including giving necessary connection to PVC pipes (including the cost of 110mm dia CI pipe for a length of 600mm) by dismantling brick masonry wall / reinforced cement concrete roof / floor slab and making good the dismantled portion to the original condition with leakages etc., complete complying with standard specifications and as | 3 | NOS | 7546.3 | 22638.9
1.41 | Paving the flooring with Ceramic tiles of size 305x305x6mm of approved quality and colour over a base layer of C.M.1:3, 20mm thick in all floors used 0.20 kg / m2 including finishing the joints and pointing flush with even surfaces etc., complete complying with standard specifications and as directed.. (The tiles should be got approved by the Executive engineer before use on works). | 16 | M2 | 1191.7 | 19067.2
1.42 | Dadooing the walls with glazed tiles of size 305mmx200mmx6mm of approved quality and colour over a base layer of C.M.1:2, 10mm and pointing the joints with white cement mixed with colouring pigment at the rate of 0.40 kg/sq.m neatly in all floors, curing etc., complete complying with standard specification and as directed by the departmental officers. (The tiles should be got approved by the Executive engineer before use on works). | 65 | M2 | 1401 | 91065
1.43 | Weathering course in brick jelly lime concrete using broken brick jelly of size 20mm uniform gauge in pure slaked lime (no sand to be used) to the proportion of brick jelly to lime being 32:12.5 by volume and laid over the RCC roof slab in a single layer of required slope and finished by beating the concrete with wooden beaters of approved pattern, keeping the surface constantly wet by sprinkling lime jaggery water, etc., complete as per standard specification and as directed by the departmental officers. | 1.5 | M3 | 6904.1 | 10356.15
1.44 | Finishing the top of roof with one course of machine pressed tiles of size 23x23x2cm laid in cement mortar 1:2 (one of cement and two of sand)mixing with water proofing compound confirming to ISS at 2% weight of cement used and pointed with water proofing compound mixed with red oxide etc., complete complying with standard specification and as directed by the departmental officers. | 21 | M2 | 1562.75 | 32817.75
1.45 | Painting new iron work with two coats of synthetic enamel paint of approved quality and colour over one coat of primer in all floors. The rate is inclusive of cost of all materials, labour charges, brushes and scaffolding charges etc. complete complying with standard specifications. (The paint should be got approved by Executive Engineer before use on works) | 10 | M2 | 174.65 | 1746.5
1.46 | Supply and fixing in position of best Indian make white / colour glazed eartherware lipped mouth flat back urinal of best quality and approved make of size 430mmx260mmx350mm with GI Pipe, 32mm dia bell mouth PVC Connection and waste pipe, 15mm dia GI Pipe of required length, 15mm dia GM Wheel valve, 15mm dia brass nipple 2 Nos and fixing the urinals in position with necessary TW plugs, Clamps, Screws etc., including dismantling masonry and redoing the same to the original condition, etc., including painting the pipe with two coats of best quality approved synthetic enamel paint over one coat of red oxide primer and checked without any leakage etc., complete complying with standard specifications and as | 2 | NOS | 2903 | 5806
1.47 | Supplying and fixing Brass Chromium platted Towel Rail 600mm Long and 20mm diameter with brackets of same materials including cost of teak wood plugs, CP Screws etc., complete complying with standard specification as directed by departmental officers. | 4 | NOS | 837 | 3348
1.48 | Construction of Manhole chamber of size 600mx600mm to a total height of 800mm ie., 200mm above ground level and 600mm below ground level with base concrete of C.C 1:5:10 of 100mm thick over a sand cushion of 100mm thick the chamber should be constructed in brick masonry of 230mm thick in cement mortar with chamber burnt bricks of size 9”x4 3/8” x2 ¾” the inner sides of chamber is plastered with cement mortar 1;3 20mm thick outer chamber to a depth of 300mm plastered with cement mortar 1:5 12mm thick, chamber is covered with SRF covere slab 100mm thick the rate including cost of all materials, labour charges etc., complete complying with standard specification and as directed by the departmental officers. | 4 | NOS | 6352 | 25408
1.49 | Supplying, and fixing PVC pipes of of 32mm dia of approved quality and variety conforming to pressure IS 4985. The rate is inclusive of cost of pipe, all taxes, conveyance charges of materials and all other labour charges for fixing the PVC pipe as directed by the departmental officers etc., complete complying with standard specifications. The PVC pipe should be got approved by the departmental officers before use on work. | 50 | RM | 350.8 | 17540
1.5 | Supplying, and fixing PVC pipes of 25mm dia of approved quality and variety conforming to pressure IS 4985. The rate is inclusive of cost of pipe, all taxes, conveyance charges of materials and all other labour charges for fixing the PVC pipe as directed by the departmental officers etc., complete complying with standard specifications. The PVC pipe should be got approved by the departmental officers before use on work | 25 | RM | 238.8 | 5970
1.51 | Supplying, and fixing PVC pipes of 110mm dia of approved quality and variety conforming to pressure IS 4985. The rate is inclusive of cost of pipe, all taxes, conveyance charges of materials and all other labour charges for fixing the PVC pipe as directed by the departmental officers etc., complete complying with standard specifications. The PVC pipe should be got approved by the departmental officers before use on work. | 20 | RM | 552 | 11040
1.52 | Supplying and fixing in position of best Indian make PVC Water Tank of 1000 litres capacity confirming to ISI standards as directed by the departmental officers including cost of material and conveyance charges of material to work site etc., complete complying with standard specifications. | 1 | NOS | 10050 | 10050
1.53 | Supply and fixing in position wash hand basin with new one fixing in position best quality approved make white glazed earthenware wash hand basin of size 550x400mm with a pair of cast iron brackets, including cost of 15mm dia metre brass chromium plated pillar tap, 32mm dia metre G.M wheel valve 15mm dia brass nipple 15mm dia nylon connection etc., including fixing the wash hand basin in the wall in position with pair of CI brackets with teak wood plugs and screws and giving necessary water supply connection and painting the brackets with two coats of paint over a primary coat of anticorrosive paint including testing for leakage etc., complete complying with standard specification. | 2 | NOS | 4636 | 9272
1.54 | Supplying and fixing in position of best approved quality of rain water down fall pipe of size 110mm dia having a pressure of 4Kg/sq.cm including cost of PVC bents, PVC shoe, cast iron gratings of required diameter and special clamps, brass screws nails etc., and fixing of cast iron gratings at junction of parapet and the junction of roof slab including finishing neatly etc., complete complying with standard specification as directed by the departmental officers. | 5 | RM | 638.7 | 3193.5
1.55 | Supplying and fixing AC ventilating shaft of 110mm dia with 3 metre height including cost of of 110mm dia AC cylindrical cowl of best approved quality etc., complete complying with standard specification and as directed by the departmental officers. | 3.5 | RM | 859.7 | 3008.95
| Sub Total = |  |  |  | 35729964.72
| GST 18% = |  |  |  | 6431393.6496
| Grand Total = |  |  |  | 42161358.3696
| Basic |  |  |  | 42169769.41
| Diff |  |  |  | -8411.0404
| % |  |  |  | -0.01995%

## Comparative
COMPARATIVE STATEMENT
Name of Work :Construction of New Taluk operational godown of 2500M.T(1X1500MT, 1X1000MT) capacity in TNCSC campus at Survey No.2347/1 to an extent of 1.21.44 Hectare at Nelliyalam Village in Pandalur Taluk in Nilgiris District.
| 450 |  |  | 3622324 |  |  | 1752324
S. No | Description of work | Agreement Rate | per | As per Agreement |  | As per Execution |  | Excess |  |  | Balance
|  |  |  | Qty | Amount | Qty | Amount | Qty | % | Amount | Qty | % | Amount
1.01 | Clearing Scrub Jungle as directed by the departmental officers. | 7.55 | M2 | 4000 | 30200 | 4000 | 30200 | 0 | 0% | 0 | 0 | 0% | 0
1.02 | EARTH WORK excavation for foundation in all classes of soils and subsoils to full depth, as may be directed except in hard rock, requiring blasting including initial leads and lifts and refilling the sides of foundation with excavated earth in 150mm layers well watered rammed and consolidated including depositing surplus earth with in the Godown or inside compound in places shown with initial leads and lifts, clearing, leveling site, shoring, strutting, baling of water wherever necessary etc., complete complying with standard specification and as directed. | 279.85 | M3 | 447 | 125092.95 | 600.06 | 167926.791 | 153.06 | 34.24% | 42833.841 | 0 | 0% | 0
1.03 | Refilling with excavated earth in basement including watering, rammed and consolidated etc., complete complying with standard specifications and as directed. | 54.55 | M3 | 273 | 14892.15 | 269.33 | 14691.9515 | 0 | 0% | 0 | 3.67 | 1.344% | 200.1985
1.04 | Supplying and filling in foundation with Gravel in layers of not exceeding 150mm thick well watered, rammed and consolidated including watering etc., complete complying with standard specification and as directed. | 2347 | M3 | 450 | 1056150 | 927.68 | 2177264.96 | 477.68 | 106.2% | 1121114.96 | 0 | 0% | 0
1.05 | Refilling with conveyed earth to a lead of 10KM for filling in foundation and basement including watering, rammed and consolidated etc., complete and as directed by the departmental officers. | 278.3 | M3 | 824 | 229319.2 | 822.94 | 229024.202 | 0 | 0% | 0 | 1.06 | 0.1286% | 294.998
1.06 | Supplying and filling in basement with wetmix 250mm thick in layers of not exceeding 250mm thick, well watered, rammed and consolidated including machineries for hire and running charges leader 5 Cum capacity, hire charges for tipper, water sprinkler,` vibratory roller all labour charges etc., complete complying with standard specification and as directed | 4269.95 | M3 | 300 | 1280985 | 209.48 | 894469.126 | 0 | 0% | 0 | 90.52 | 30.17% | 386515.874
1.07 | CEMENT CONCRETE 1:5:10(one cement , five sand and ten aggregate)using 40mm gauge hard broken granite stone jelly for foundation including de-watering side shuttering , strutting, wherever necessary including curing etc., complete complying with standard specifications and as directed. | 8093 | M3 | 270 | 2185110 | 247.39 | 2002127.27 | 0 | 0% | 0 | 22.61 | 8.374% | 182982.73
1.08 | BRICK WORK in cement mortar 1:5(One cement ,Five sand)using best quality Country Bricks of size 8 ¾”x4 ¼” x2¼’’ for walls including cost of scaffolding curing ,finishing etc., complete complying with standard specifications and as directed. In foundation and basement. | 7536.75 | M3 | 141 | 1062681.75 | 181.41 | 1367241.8175 | 40.41 | 28.66% | 304560.0675 | 0 | 0% | 0
1.09 | In ground floor Upto 4.50M height above basement. | 7647.2 | M3 | 243 | 1858269.6 | 273.48 | 2091356.256 | 30.48 | 12.54% | 233086.656 | 0 | 0% | 0
1.1 | Above 4.50M height above basement. | 7870.19 | M3 | 103 | 810629.57 | 81.18 | 638902.0242 | 0 | 0% | 0 | 21.82 | 21.18% | 171727.5458
1.11 | Providing FORM WORK for centering the soffits of all reinforcement concrete work including strutting to the required (3 metre) height with mild-steel sheets of size 90cmx60cm 10 gauge stiffened with welded mild steel angles of size 25mmx25mmx3mm laid with country wood joist of average of size 10cmx6.50cm at about 90cm centres with casurina props of 13cm dia at 75cm centre to centre with all nails coir,wedges complete and removing the form work after necessary curing period as directed by the corporations officers. The rates should inclusives of cutting , bending, welding , charges of M.S sheets, M.S. angles etc., Complete Column footing, Plinth beam, top tie beame | 1159.9 | M2 | 715 | 829328.5 | 743.97 | 862930.803 | 28.97 | 4.052% | 33602.303 | 0 | 0% | 0
1.12 | Rectangular beams and floor slabs, tie beams, lintels, landing slab, loft etc., | 1278.8 | M2 | 805 | 1029434 | 758.4 | 969841.92 | 0 | 0% | 0 | 46.6 | 5.789% | 59592.08 | 121.75
1.13 | Column, ratguard slab, curtain slab and sun shades etc., | 1406.65 | M2 | 906 | 1274424.9 | 953.6 | 1341381.44 | 47.6 | 5.254% | 66956.54 | 0 | 0% | 0
1.14 | Supplying, fabricating and placing in position MS/RTS grills for reinforcement for all R.C.C.works including cost of steel, labour for straightening, bending, cranking, tying grills with 18 gauge galvanized binding wire and placing grills in position complete complying with standard specification and as directed.. | 10099.75 | QTL | 524.6 | 5298328.85 | 388.2612 | 3921341.2688 | 0 | 0% | 0 | 136.3388 | 25.99% | 1376987.5812
1.15 | Supplying and fixing (under lintel grove) cold rolled ROLLING SHUTTERS of approved quality of 18 gauge 7.5 cm wide cold rolled lathe section in one piece interlocked together with specially designed pipe shaft with adequate number of high tensile steels wire springs of approved quality complete with brackets side guides and arrangements for inside and outside locking arrangements with push and pull operations and pulling back handle with all accessories without workmanship and the entire shutter painted with two coats of best quality anti-corrosive nut brown color paint over one coat of red oxide primer and clear opening of 1.8 M width 2.60 M | 14635 | NOS | 10 | 146350 | 12 | 175620 | 2 | 20% | 29270 | 0 | 0% | 0
1.16 | Supplying and fixing of Steel glazed AIR INLET WINDOWs of size 0.6m x 0.6m using extruded angles (Z-section) alround for frame with centre mullion (T-section) and shutter with the same Z-section properly fixed with hinges 2 nos. for each shutter. The panel of shutter fixed with G.I. sheet of'18 gauge and necessary locking arrangements including weld mesh cover using weld mesh 25mm x 25mm x 10mm gauge and welded with iron square bars of 10mm size - 3nos. horizontally and 2nos. vertically welded together to form a grill and welding grill to the main frame with 4mm thick and 12mm wide MS flats. The rate is also inclusive of one coat of steel primer and two coats of ANTI CORROSIVE METALLIC paint and quality, 2 nos. | 3453.2 | NOS | 36 | 124315.2 | 34 | 117408.8 | 0 | 0% | 0 | 2 | 5.556% | 6906.4
1.17 | Supplying and fixing steel N-Type VENTILATOR of size 2.60m x 0.60m using extruded angle (Z-section 25mmx25mmx3mm) for outer frames with center mullion (T-section)and with weld mesh of 25mmx25mm 10guage on all three sides ( 2 verticals 1 horizontal) and 10mm size MS square bars horizontally one at top and one at bottom welded to the frames with necessary MS flats of size 20mmx4mm thick | 4250 | NOS | 92 | 391000 | 92 | 391000 | 0 | 0% | 0 | 0 | 0% | 0
1.18 | Providing vacuum de watered controlled cement surfacing 100mm thick in required slope and chamber confirming M20 grade with 20mm size stone aggregate cast in situ ,smooth finish and leveling with double framed screed vibrator ,excess water to be removed through vacuum pump with bottom and top filter mat duly sealing the edges all round including provisions of polythene sheet below the concrete layer before placing of concrete and finishing with paver floated and power trawler to obtain the hard surface including provision of expansion joints at 6mtr intervals across the platform by cutting 6mm wide and full depth of concrete by contractors | 1653.4 | M2 | 1503 | 2485060.2 | 1503.594 | 2486042.3196 | 0.594 | 0.03952% | 982.1196 | 0 | 0% | 0
1.19 | PLASTERING with cement mortor 1:5 (one cement and five sand) 12mm thick including cost of scaffolding, finishing, curing etc., complete complying with standard specification and as directed. | 356.05 | M2 | 3522 | 1254008.1 | 3729.57 | 1327913.3985 | 207.57 | 5.894% | 73905.2985 | 0 | 0% | 0
1.2 | PLASTERING with the exposed RCC surface with C.M.1:3(one cement and three sand) 10mm thick including cost of scaffolding, finishing, curing etc., complete complying with standard Specification and as directed. | 401.1 | M2 | 1350 | 541485 | 1433.66 | 575041.026 | 83.66 | 6.197% | 33556.026 | 0 | 0% | 0
1.21 | Painting the walls with two coats of exterior emulsion paint of first class approved quality and colour over a priming coat including thorough scrapping, clean removal of dirt, and including necessary plaster of paris putty, wherever required etc., complete complying with standard specification and as directed. | 309.2 | M2 | 3209 | 992222.8 | 3040.59 | 940150.428 | 0 | 0% | 0 | 168.41 | 5.248% | 52072.372
1.22 | Supplying, fabricating and fixing in position M.S.Channel 100x50x6mm at the edge of loading platform with M.S bolt of 16mm at the edge of loading platform with M.S bolt of 16mm at the edge of loading platform finishing in flush with the slab with C.M 1:3 complete including painting the exposed surface of MS channel with two coats of ANI Corrosive metalic net brown colour paint over one coat red oxide primer etc., complete. | 1277 | RM | 76.4 | 97562.8 | 81.5 | 104075.5 | 5.1 | 6.675% | 6512.7 | 0 | 0% | 0
1.23 | Supplying and fixing of Rotary Ventilators over the roof with necessary bolt and nut arrangement to withstand the wind velocity as specified by the departmental officers. (Size 600mm x 600mm) | 18000 | NOS | 11 | 198000 | 11 | 198000 | 0 | 0% | 0 | 0 | 0% | 0
1.24 | Supplying and laying of profiled colour galvalume sheet with combination 55A1:43 4Zn:1:6SI of TCT bent type 0.47mm thick and standard width of 1.06m with yield strength of 550 MPA made from high tensile/ CR sheets of approved quality for roofing with necessary fixing arrangements like 65m abd long hexagonal head screws with EPDM rubber seal etc., complete complying with standard specification and as directed by the departmental officer. (Test certificate for quality should be furnished on receipt of material at site) | 1198.15 | M2 | 1911 | 2289664.65 | 1897.96 | 1591828.5418 | 0 | 0% | 0 | 13.04 | 0.6824% | 15623.876
1.25 | Supplying and roofing with Galvalume sheet ridge pieces of size 1.00M x 0.7M, 0.47mm thick with necessary U or J bolt and nuts G.I washers etc., complete For the above works skilled man power, necessary tools, equipments, power supply, water supply including transport, any other statuary approval required for the transporting the materials shall be duly obtained by the contractor. (Test certificate for quality should be furnished on receipt of material at site) | 656.5 | RM | 107 | 70245.5 | 105.92 | 48675.536 | 0 | 0% | 0 | 1.08 | 1.009% | 709.02
1.26 | Supplying and fixing corrugated Poly Carbonate sheet of size 3mx1.06m of 3mm thick on the roof in-between the colour coated Galvalume sheets for proper lighting with necessary G.I screws and EPDM rubber washers, Complying with standard specification and as direct and specified by the departmental officers including cost of loading unloading and transportion charges etc., complete. | 1427.85 | M2 | 34 | 48546.9 | 33 | 47119.05 | 0 | 0% | 0 | 1 | 2.941% | 1427.85
1.27 | Painting the walls with two coats of oil bound distemper over one coat of water based cement primer including cost of distemper, primer, cleaning, scrabbing the walls, rendering the walls smooth with necessary putty, brushes, scaffolding arrangements, labour charges etc., complete, complying standard specification and as directed. ( The quality and colour of oil bound distemper should got approved by the Executive Engineer before use.) | 197.75 | M2 | 1865 | 368803.75 | 1802.31 | 356406.8025 | 0 | 0% | 0 | 62.69 | 3.361% | 12396.9475
1.28 | Supplying and fixing of 40 X 6mm G.I Flat over the galvalume sheet roofing which is placed on the top of Purlin in the longitudinal direction to avoid the lifting of roofing during heavy wind. The rate is inclusive of GI screws 75mm length with rubber and aluminium washer, drilling hole over GI Flat to hold the sheet and purlin with necessary adhesive flashing tap directly over the galvalume sheet including labour charges for fixing, conveyance, loading, unloading and cutting etc. complete as directed by the departmental officers. | 241.35 | RM | 842 | 203216.7 | 840 | 202734 | 0 | 0% | 0 | 2 | 0.2375% | 482.7
1.29 | Supplying fabricating, hoisting and erection of ROOF TRUSSES PURLINS AND WIND BRACING with structural steel member like angle and channel iron and M.S.plates for all truss, purlin members including all cutting drilling holes, and welding and fixing of member with necessary bolts and nuts, of approved quality and hoisting, aligning and placing the trusses in position etc., complete the trusses will be manufactured as per the detailed plan. The rate should include the cost of painting with one coat of red oxide primer with two coats of best quality of aluminium paint over priming coat. | 145.2 | Kg | 35811 | 5199757.2 | 35731 | 3631698.84 | 0 | 0% | 0 | 80 | 0.2234% | 11616
1.3 | Reinforcement Cement Concrete 1:1 ½ :3 ( one cement, one and half sand, three aggregate) using 20mm of hard broken granite stone for all RCC works using machine for mixing concrete excluding cost of centering, Strutting, shuttering, and fabrication of reinforcement and placing the grills in position etc., but including finishing and curing etc., complete complying with standard specifications and as directed. In foundation and basement | 12500.45 | M3 | 154 | 1925069.3 | 230.03 | 2875478.5135 | 76.03 | 49.37% | 950409.2135 | 0 | 0% | 0
1.31 | In ground floor Upto 4.50M height above basement. | 12668.25 | M3 | 72 | 912114 | 81.88 | 1037276.31 | 9.88 | 13.72% | 125162.31 | 0 | 0% | 0
1.32 | Above 4.50M height from basement | 12998.75 | M3 | 69 | 896913.75 | 64.19 | 834389.7625 | 0 | 0% | 0 | 4.81 | 6.971% | 62523.9875
1.33 | Supplying and filling in foundation, basement, etc., with filling crushed stone sand in layers of not more than 15cm thick well watered, rammed and consolidated etc., complete complying with standard specification and as directed by the departmental officers. | 3455.65 | M3 | 16 | 55290.4 | 15.014 | 51883.1291 | 0 | 0% | 0 | 0.986 | 6.163% | 3407.2709
1.34 | Cement Concrete 1:2:4 ( one cement, two sand, four aggregate) using 20mm of hard broken granite stone for all RCC works using machine for mixing concrete excluding cost of centering, Strutting, shuttering, and fabrication of reinforcement and placing the grills in position etc., but including finishing and curing etc., complete complying with standard specifications and as directed. In foundation basement | 11812.25 | M3 | 6 | 70873.5 | 7.142 | 84363.0895 | 1.142 | 19.03% | 13489.5895 | 0 | 0% | 0
1.35 | In ground floor upto 4.50M height above basement | 11980 | M3 | 5 | 59900 | 7.95 | 95241 | 2.95 | 59% | 35341 | 0 | 0% | 0
1.36 | Supplying and fixing in position of rain beating RCC Jolly, 5 cm thick in cement concrete 1:2:4 using 20mm stone jelly, including cost and conveyance of all materials labour charges for mixing, laying, casting, curing and fixing in position of jolly as directed and cost of mould, fabrication of reinforcement, etc., complete. | 1514.45 | M2 | 3 | 4543.35 | 0 | 0 | 0 | 0% | 0 | 3 | 100% | 4543.35
1.37 | Supplying and fixing of UPVC ventilator (Up-plasticized poly vinyl choloride) louvered ventilators of form profile size outer frame 60x58 mm and shutter profile size 60 x78mm both profiles reinforced with GI 1mm 125 GSM and 100% corrosion free multi colored chamber section with wall thick of 2mm. The EPDM rubber (Black colour ) covered with all the edges frame shutters. The corners and joints to be welded and cleaned. Radiation pin headed glass 4mm thick should be provided to the louvers. The Ventilator should be fixed to the wall with 100% packing with screws silicon packing round the frames. The Ventilator should got approved from Executive Engineer. | 8106 | M2 | 1.2 | 9727.2 | 0 | 0 | 0 | 0% | 0 | 1.2 | 100% | 9727.2
1.38 | Supplying and fixing M.S Grill to special windows and ventilators etc using 20mmx6mm angle including cost of MS grill, one of red oxide and fixing in position etc. complete complying with Standard Specification and as directed. | 114.95 | KG | 100 | 11495 | 0 | 0 | 0 | 0% | 0 | 100 | 100% | 11495
1.39 | Fabricating, supplying and fixing in position of SOLID PVC DOORS with frames of sizes as per the specifications given below: PVC door frames made out of best quality PVC extruded section of 40mm * 58 mm * 2.50 mm +/- 0.3 mm thick, having multi chamber cross section and duly reinforced with steel to be mitre cut at the corners and welded including providing tie rod at the bottom and necessary weather seal etc., and PVC door shutters made out of extruded plastic section of 60 mm * 24 mm size in the configuration of an “A” section for shutter frames and multi-chamber hollow plastic section of 200 mm 200 mm1 mm (average thickness) with tongue and groove section for panels etc., with necessary holdfasts, rubber beedings, furniture fittings, locking | 3325 | NOS | 5 | 16625 | 0 | 0 | 0 | 0% | 0 | 5 | 100% | 16625
1.4 | Supplying and fixing in position Indian Water Closet (Oriya type) of size 580 x 440mm white glazed earthern ware of approved quality and brand with "P" or "S" trap conforming to BIS with sand cushion and forming flooring alround the closet using 40mm broken brick jelly in lime concrete 1:2:5 (One lime, Two sand and Five brick jelly) 100mm thick and finishing the top to the required slope and including giving necessary connection to PVC pipes (including the cost of 110mm dia CI pipe for a length of 600mm) by dismantling brick masonry wall / reinforced cement concrete roof / floor slab and making good the dismantled portion to the original condition with leakages etc., complete complying with standard specifications and as | 7546.3 | NOS | 3 | 22638.9 | 0 | 0 | 0 | 0% | 0 | 3 | 100% | 22638.9
1.41 | Paving the flooring with Ceramic tiles of size 305x305x6mm of approved quality and colour over a base layer of C.M.1:3, 20mm thick in all floors used 0.20 kg / m2 including finishing the joints and pointing flush with even surfaces etc., complete complying with standard specifications and as directed.. (The tiles should be got approved by the Executive engineer before use on works). | 1191.7 | M2 | 16 | 19067.2 | 0 | 0 | 0 | 0% | 0 | 16 | 100% | 19067.2
1.42 | Dadooing the walls with glazed tiles of size 305mmx200mmx6mm of approved quality and colour over a base layer of C.M.1:2, 10mm and pointing the joints with white cement mixed with colouring pigment at the rate of 0.40 kg/sq.m neatly in all floors, curing etc., complete complying with standard specification and as directed by the departmental officers. (The tiles should be got approved by the Executive engineer before use on works). | 1401 | M2 | 65 | 91065 | 0 | 0 | 0 | 0% | 0 | 65 | 100% | 91065
1.43 | Weathering course in brick jelly lime concrete using broken brick jelly of size 20mm uniform gauge in pure slaked lime (no sand to be used) to the proportion of brick jelly to lime being 32:12.5 by volume and laid over the RCC roof slab in a single layer of required slope and finished by beating the concrete with wooden beaters of approved pattern, keeping the surface constantly wet by sprinkling lime jaggery water, etc., complete as per standard specification and as directed by the departmental officers. | 6904.1 | M3 | 1.5 | 10356.15 | 0 | 0 | 0 | 0% | 0 | 1.5 | 100% | 10356.15
1.44 | Finishing the top of roof with one course of machine pressed tiles of size 23x23x2cm laid in cement mortar 1:2 (one of cement and two of sand)mixing with water proofing compound confirming to ISS at 2% weight of cement used and pointed with water proofing compound mixed with red oxide etc., complete complying with standard specification and as directed by the departmental officers. | 1562.75 | M2 | 21 | 32817.75 | 0 | 0 | 0 | 0% | 0 | 21 | 100% | 32817.75
1.45 | Painting new iron work with two coats of synthetic enamel paint of approved quality and colour over one coat of primer in all floors. The rate is inclusive of cost of all materials, labour charges, brushes and scaffolding charges etc. complete complying with standard specifications. (The paint should be got approved by Executive Engineer before use on works) | 174.65 | M2 | 10 | 1746.5 | 0 | 0 | 0 | 0% | 0 | 10 | 100% | 1746.5
1.46 | Supply and fixing in position of best Indian make white / colour glazed eartherware lipped mouth flat back urinal of best quality and approved make of size 430mmx260mmx350mm with GI Pipe, 32mm dia bell mouth PVC Connection and waste pipe, 15mm dia GI Pipe of required length, 15mm dia GM Wheel valve, 15mm dia brass nipple 2 Nos and fixing the urinals in position with necessary TW plugs, Clamps, Screws etc., including dismantling masonry and redoing the same to the original condition, etc., including painting the pipe with two coats of best quality approved synthetic enamel paint over one coat of red oxide primer and checked without any leakage etc., complete complying with standard specifications and as | 2903 | NOS | 2 | 5806 | 0 | 0 | 0 | 0% | 0 | 2 | 100% | 5806
1.47 | Supplying and fixing Brass Chromium platted Towel Rail 600mm Long and 20mm diameter with brackets of same materials including cost of teak wood plugs, CP Screws etc., complete complying with standard specification as directed by departmental officers. | 837 | NOS | 4 | 3348 | 0 | 0 | 0 | 0% | 0 | 4 | 100% | 3348
1.48 | Construction of Manhole chamber of size 600mx600mm to a total height of 800mm ie., 200mm above ground level and 600mm below ground level with base concrete of C.C 1:5:10 of 100mm thick over a sand cushion of 100mm thick the chamber should be constructed in brick masonry of 230mm thick in cement mortar with chamber burnt bricks of size 9”x4 3/8” x2 ¾” the inner sides of chamber is plastered with cement mortar 1;3 20mm thick outer chamber to a depth of 300mm plastered with cement mortar 1:5 12mm thick, chamber is covered with SRF covere slab 100mm thick the rate including cost of all materials, labour charges etc., complete complying with standard specification and as directed by the departmental officers. | 6352 | NOS | 4 | 25408 | 0 | 0 | 0 | 0% | 0 | 4 | 100% | 25408
1.49 | Supplying, and fixing PVC pipes of of 32mm dia of approved quality and variety conforming to pressure IS 4985. The rate is inclusive of cost of pipe, all taxes, conveyance charges of materials and all other labour charges for fixing the PVC pipe as directed by the departmental officers etc., complete complying with standard specifications. The PVC pipe should be got approved by the departmental officers before use on work. | 350.8 | RM | 50 | 17540 | 0 | 0 | 0 | 0% | 0 | 50 | 100% | 17540
1.5 | Supplying, and fixing PVC pipes of 25mm dia of approved quality and variety conforming to pressure IS 4985. The rate is inclusive of cost of pipe, all taxes, conveyance charges of materials and all other labour charges for fixing the PVC pipe as directed by the departmental officers etc., complete complying with standard specifications. The PVC pipe should be got approved by the departmental officers before use on work | 238.8 | RM | 25 | 5970 | 0 | 0 | 0 | 0% | 0 | 25 | 100% | 5970
1.51 | Supplying, and fixing PVC pipes of 110mm dia of approved quality and variety conforming to pressure IS 4985. The rate is inclusive of cost of pipe, all taxes, conveyance charges of materials and all other labour charges for fixing the PVC pipe as directed by the departmental officers etc., complete complying with standard specifications. The PVC pipe should be got approved by the departmental officers before use on work. | 552 | RM | 20 | 11040 | 0 | 0 | 0 | 0% | 0 | 20 | 100% | 11040
1.52 | Supplying and fixing in position of best Indian make PVC Water Tank of 1000 litres capacity confirming to ISI standards as directed by the departmental officers including cost of material and conveyance charges of material to work site etc., complete complying with standard specifications. | 10050 | NOS | 1 | 10050 | 0 | 0 | 0 | 0% | 0 | 1 | 100% | 10050
1.53 | Supply and fixing in position wash hand basin with new one fixing in position best quality approved make white glazed earthenware wash hand basin of size 550x400mm with a pair of cast iron brackets, including cost of 15mm dia metre brass chromium plated pillar tap, 32mm dia metre G.M wheel valve 15mm dia brass nipple 15mm dia nylon connection etc., including fixing the wash hand basin in the wall in position with pair of CI brackets with teak wood plugs and screws and giving necessary water supply connection and painting the brackets with two coats of paint over a primary coat of anticorrosive paint including testing for leakage etc., complete complying with standard specification. | 4636 | NOS | 2 | 9272 | 0 | 0 | 0 | 0% | 0 | 2 | 100% | 9272
1.54 | Supplying and fixing in position of best approved quality of rain water down fall pipe of size 110mm dia having a pressure of 4Kg/sq.cm including cost of PVC bents, PVC shoe, cast iron gratings of required diameter and special clamps, brass screws nails etc., and fixing of cast iron gratings at junction of parapet and the junction of roof slab including finishing neatly etc., complete complying with standard specification as directed by the departmental officers. | 638.7 | RM | 5 | 3193.5 | 0 | 0 | 0 | 0% | 0 | 5 | 100% | 3193.5
1.55 | Supplying and fixing AC ventilating shaft of 110mm dia with 3 metre height including cost of of 110mm dia AC cylindrical cowl of best approved quality etc., complete complying with standard specification and as directed by the departmental officers. | 859.7 | RM | 3.5 | 3008.95 | 0 | 0 | 0 | 0% | 0 | 3.5 | 100% | 3008.95
| Sub Total = |  |  |  | 35729964.72 |  | 33881045.877 |  |  | 3070782.6246 |  |  | 2660185.9314
| GST 18% = |  |  |  | 6431393.6496 |  | 6098588.2579 |  |  | 552740.8724 |  |  | 478833.4676
| Grand Total = |  |  |  | 42161358.3696 |  | 39979634.1349 |  |  | 3623523.497 |  |  | 3139019.399
CERTIFICATES
1 | Certified that the work is in Progress. | [5 empty] | 2181724.2347
2 | Certified that there is no recovery due from the contractor
3 | Certified that the contractor has engaged the Technical Assistant for supervising the work during execution.
4 | Certified that the contractor has utilized the cement,steel, of required quantity of good quality to this work.
| Asst Engineer |  |  | Asst. Exe. Engineer | [5 empty] | Exe. Engineer
| TNCSC Coimbatore |  |  | TNCSC Coimbatore | [5 empty] | TNCSC Chennai

## Bill Abs
LS 3rd & Final Bill
Name of Work :Construction of New Taluk operational godown of 2500M.T(1X1500MT, 1X1000MT) capacity in TNCSC campus at Survey No.2347/1 to an extent of 1.21.44 Hectare at Nelliyalam Village in Pandalur Taluk in Nilgiris District.
| 450 |  |  | 3622324 |  |  | 1752324
| Name of the Contractor:- M/s .Romaa Housing Pvt Ltd, Chennai. |  |  | Date of commencement : 12 .09 .2024 |  |  | Agreement Period : 12 months Probable Completion : 11.9.2025
S.NO | DISCRIPTION OF WORK | Total Qty Upto date |  | Agt Rate | Total Value Upto Date (In Rupees) | Deduct Previous Bill Amount |  |  | Since Last Measurements |  |  | Agreement Qty
|  | Qty | Unit |  |  | M.Book/ Pg | Qty | Ampount (in Rupees) | QTY | Unit | Amount (in Rupees)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1.01 | Clearing Scrub Jungle as directed by the departmental officers. | 4000 | M2 | 7.55 | 30200 | 0 | 4000 | 30200 |  | M2 | 0 | 4000
1.02 | EARTH WORK excavation for foundation in all classes of soils and subsoils to full depth, as may be directed except in hard rock, requiring blasting including initial leads and lifts and refilling the sides of foundation with excavated earth in 150mm layers well watered rammed and consolidated including depositing surplus earth with in the Godown or inside compound in places shown with initial leads and lifts, clearing, leveling site, shoring, strutting, baling of water wherever necessary etc., complete complying with standard specification and as directed. | 600.06 | M3 | 279.85 | 167926.791 | 0 | 566.32 | 158484.652 | 33.74 | M3 | 9442.139 | 447
1.03 | Refilling with excavated earth in basement including watering, rammed and consolidated etc., complete complying with standard specifications and as directed. | 269.33 | M3 | 54.55 | 14691.9515 | 0 | 269.33 | 14691.9515 |  | M3 | 0 | 273
1.04 | Supplying and filling in foundation with Gravel in layers of not exceeding 150mm thick well watered, rammed and consolidated including watering etc., complete complying with standard specification and as directed. | 927.68 | M3 | 2347 | 2177264.96 | 0 | 927.68 | 2177264.96 |  | M3 | 0 | 450
1.05 | Refilling with conveyed earth to a lead of 10KM for filling in foundation and basement including watering, rammed and consolidated etc., complete and as directed by the departmental officers. | 822.94 | M3 | 278.3 | 229024.202 | 0 | 822.94 | 229024.202 |  | M3 | 0 | 824
1.06 | Supplying and filling in basement with wetmix 250mm thick in layers of not exceeding 250mm thick, well watered, rammed and consolidated including machineries for hire and running charges leader 5 Cum capacity, hire charges for tipper, water sprinkler,` vibratory roller all labour charges etc., complete complying with standard specification and as directed | 209.48 | M3 | 4269.95 | 894469.126 | 0 | 209.48 | 894469.126 |  | M3 | 0 | 300
1.07 | CEMENT CONCRETE 1:5:10(one cement , five sand and ten aggregate)using 40mm gauge hard broken granite stone jelly for foundation including de-watering side shuttering , strutting, wherever necessary including curing etc., complete complying with standard specifications and as directed. | 247.39 | M3 | 8093 | 2002127.27 | 0 | 173.76 | 1406239.68 | 73.63 | M3 | 595887.59 | 270
1.08 | BRICK WORK in cement mortar 1:5(One cement ,Five sand)using best quality Country Bricks of size 8 ¾”x4 ¼” x2¼’’ for walls including cost of scaffolding curing ,finishing etc., complete complying with standard specifications and as directed. In foundation and basement. | 181.41 | M3 | 7536.75 | 1367241.8175 | 0 | 181.41 | 1367241.8175 |  | M3 | 0 | 141
1.09 | In ground floor Upto 4.50M height above basement. | 273.48 | M3 | 7647.2 | 2091356.256 | 0 | 247.35 | 1891534.92 | 26.13 | M3 | 199821.336 | 243
1.1 | Above 4.50M height above basement. | 81.18 | M3 | 7870.19 | 638902.0242 | 0 | 81.18 | 638902.0242 |  | M3 | 0 | 103
1.11 | Providing FORM WORK for centering the soffits of all reinforcement concrete work including strutting to the required (3 metre) height with mild-steel sheets of size 90cmx60cm 10 gauge stiffened with welded mild steel angles of size 25mmx25mmx3mm laid with country wood joist of average of size 10cmx6.50cm at about 90cm centres with casurina props of 13cm dia at 75cm centre to centre with all nails coir,wedges complete and removing the form work after necessary curing period as directed by the corporations officers. The rates should inclusives of cutting , bending, welding , charges of M.S sheets, M.S. angles etc., Complete Column footing, Plinth beam, top tie beame | 743.97 | M2 | 1159.9 | 862930.803 | 0 | 743.97 | 862930.803 |  | M2 | 0 | 715
1.12 | Rectangular beams and floor slabs, tie beams, lintels, landing slab, loft etc., | 758.4 | M2 | 1278.8 | 969841.92 | 0 | 661.02 | 845312.376 | 97.38 | M2 | 124529.544 | 805
1.13 | Column, ratguard slab, curtain slab and sun shades etc., | 953.6 | M2 | 1406.65 | 1341381.44 | 0 | 953.6 | 1341381.44 |  | M2 | 0 | 906
1.14 | Supplying, fabricating and placing in position MS/RTS grills for reinforcement for all R.C.C.works including cost of steel, labour for straightening, bending, cranking, tying grills with 18 gauge galvanized binding wire and placing grills in position complete complying with standard specification and as directed.. | 388.2612 | QTL | 10099.75 | 3921341.2688 | 0 | 388.2612 | 3921341.2688 | 0 | QTL | 0 | 524.6
1.15 | Supplying and fixing (under lintel grove) cold rolled ROLLING SHUTTERS of approved quality of 18 gauge 7.5 cm wide cold rolled lathe section in one piece interlocked together with specially designed pipe shaft with adequate number of high tensile steels wire springs of approved quality complete with brackets side guides and arrangements for inside and outside locking arrangements with push and pull operations and pulling back handle with all accessories without workmanship and the entire shutter painted with two coats of best quality anti-corrosive nut brown color paint over one coat of red oxide primer and clear opening of 1.8 M width 2.60 M | 12 | NOS | 14635 | 175620 | 0 | 12 | 175620 |  | NOS | 0 | 10
1.16 | Supplying and fixing of Steel glazed AIR INLET WINDOWs of size 0.6m x 0.6m using extruded angles (Z-section) alround for frame with centre mullion (T-section) and shutter with the same Z-section properly fixed with hinges 2 nos. for each shutter. The panel of shutter fixed with G.I. sheet of'18 gauge and necessary locking arrangements including weld mesh cover using weld mesh 25mm x 25mm x 10mm gauge and welded with iron square bars of 10mm size - 3nos. horizontally and 2nos. vertically welded together to form a grill and welding grill to the main frame with 4mm thick and 12mm wide MS flats. The rate is also inclusive of one coat of steel primer and two coats of ANTI CORROSIVE METALLIC paint and quality, 2 nos. | 34 | NOS | 3453.2 | 117408.8 | 0 | 34 | 117408.8 |  | NOS | 0 | 36
1.17 | Supplying and fixing steel N-Type VENTILATOR of size 2.60m x 0.60m using extruded angle (Z-section 25mmx25mmx3mm) for outer frames with center mullion (T-section)and with weld mesh of 25mmx25mm 10guage on all three sides ( 2 verticals 1 horizontal) and 10mm size MS square bars horizontally one at top and one at bottom welded to the frames with necessary MS flats of size 20mmx4mm thick | 92 | NOS | 4250 | 391000 | 0 | 92 | 391000 |  | NOS | 0 | 92
1.18 | Providing vacuum de watered controlled cement surfacing 100mm thick in required slope and chamber confirming M20 grade with 20mm size stone aggregate cast in situ ,smooth finish and leveling with double framed screed vibrator ,excess water to be removed through vacuum pump with bottom and top filter mat duly sealing the edges all round including provisions of polythene sheet below the concrete layer before placing of concrete and finishing with paver floated and power trawler to obtain the hard surface including provision of expansion joints at 6mtr intervals across the platform by cutting 6mm wide and full depth of concrete by contractors | 1503.594 | M2 | 1653.4 | 2486042.3196 | 0 | 0 | 0 | 1503.594 | M2 | 2486042.3196 | 1503
1.19 | PLASTERING with cement mortor 1:5 (one cement and five sand) 12mm thick including cost of scaffolding, finishing, curing etc., complete complying with standard specification and as directed. | 3729.57 | M2 | 356.05 | 1327913.3985 | 0 | 1480.4 | 527096.42 | 2249.17 | M2 | 800816.9785 | 3522
1.2 | PLASTERING with the exposed RCC surface with C.M.1:3(one cement and three sand) 10mm thick including cost of scaffolding, finishing, curing etc., complete complying with standard Specification and as directed. | 1433.66 | M2 | 401.1 | 575041.026 | 0 | 539.81 | 216517.791 | 893.85 | M2 | 358523.235 | 1350
1.21 | Painting the walls with two coats of exterior emulsion paint of first class approved quality and colour over a priming coat including thorough scrapping, clean removal of dirt, and including necessary plaster of paris putty, wherever required etc., complete complying with standard specification and as directed. | 3040.59 | M2 | 309.2 | 940150.428 | 0 | 0 | 0 | 3040.59 | M2 | 940150.428 | 3209
1.22 | Supplying, fabricating and fixing in position M.S.Channel 100x50x6mm at the edge of loading platform with M.S bolt of 16mm at the edge of loading platform with M.S bolt of 16mm at the edge of loading platform finishing in flush with the slab with C.M 1:3 complete including painting the exposed surface of MS channel with two coats of ANI Corrosive metalic net brown colour paint over one coat red oxide primer etc., complete. | 81.5 | RM | 1277 | 104075.5 | 0 | 81.5 | 104075.5 |  | RM | 0 | 76.4
1.23 | Supplying and fixing of Rotary Ventilators over the roof with necessary bolt and nut arrangement to withstand the wind velocity as specified by the departmental officers. (Size 600mm x 600mm) | 11 | NOS | 18000 | 198000 | 0 | 0 | 0 | 11 | NOS | 198000 | 11
1.24 | Supplying and laying of profiled colour galvalume sheet with combination 55A1:43 4Zn:1:6SI of TCT bent type 0.47mm thick and standard width of 1.06m with yield strength of 550 MPA made from high tensile/ CR sheets of approved quality for roofing with necessary fixing arrangements like 65m abd long hexagonal head screws with EPDM rubber seal etc., complete complying with standard specification and as directed by the departmental officer. (Test certificate for quality should be furnished on receipt of material at site) | 1897.96 | M2 | 838.705 | 1591828.5418 | 0 | 1897.96 | 1591828.5418 |  | M2 | 0 | 1911
1.25 | Supplying and roofing with Galvalume sheet ridge pieces of size 1.00M x 0.7M, 0.47mm thick with necessary U or J bolt and nuts G.I washers etc., complete For the above works skilled man power, necessary tools, equipments, power supply, water supply including transport, any other statuary approval required for the transporting the materials shall be duly obtained by the contractor. (Test certificate for quality should be furnished on receipt of material at site) | 105.92 | RM | 459.55 | 48675.536 | 0 | 105.92 | 48675.536 |  | RM | 0 | 107
1.26 | Supplying and fixing corrugated Poly Carbonate sheet of size 3mx1.06m of 3mm thick on the roof in-between the colour coated Galvalume sheets for proper lighting with necessary G.I screws and EPDM rubber washers, Complying with standard specification and as direct and specified by the departmental officers including cost of loading unloading and transportion charges etc., complete. | 33 | M2 | 1427.85 | 47119.05 | 0 | 0 | 0 | 33 | M2 | 47119.05 | 34
1.27 | Painting the walls with two coats of oil bound distemper over one coat of water based cement primer including cost of distemper, primer, cleaning, scrabbing the walls, rendering the walls smooth with necessary putty, brushes, scaffolding arrangements, labour charges etc., complete, complying standard specification and as directed. ( The quality and colour of oil bound distemper should got approved by the Executive Engineer before use.) | 1802.31 | M2 | 197.75 | 356406.8025 | 0 | 0 | 0 | 1802.31 | M2 | 356406.8025 | 1865
1.28 | Supplying and fixing of 40 X 6mm G.I Flat over the galvalume sheet roofing which is placed on the top of Purlin in the longitudinal direction to avoid the lifting of roofing during heavy wind. The rate is inclusive of GI screws 75mm length with rubber and aluminium washer, drilling hole over GI Flat to hold the sheet and purlin with necessary adhesive flashing tap directly over the galvalume sheet including labour charges for fixing, conveyance, loading, unloading and cutting etc. complete as directed by the departmental officers. | 840 | RM | 241.35 | 202734 | 0 | 0 | 0 | 840 | RM | 202734 | 842
1.29 | Supplying fabricating, hoisting and erection of ROOF TRUSSES PURLINS AND WIND BRACING with structural steel member like angle and channel iron and M.S.plates for all truss, purlin members including all cutting drilling holes, and welding and fixing of member with necessary bolts and nuts, of approved quality and hoisting, aligning and placing the trusses in position etc., complete the trusses will be manufactured as per the detailed plan. The rate should include the cost of painting with one coat of red oxide primer with two coats of best quality of aluminium paint over priming coat. | 35731 | Kg | 101.64 | 3631698.84 | 0 | 35731 | 3631698.84 |  | Kg | 0 | 35811
1.3 | Reinforcement Cement Concrete 1:1 ½ :3 ( one cement, one and half sand, three aggregate) using 20mm of hard broken granite stone for all RCC works using machine for mixing concrete excluding cost of centering, Strutting, shuttering, and fabrication of reinforcement and placing the grills in position etc., but including finishing and curing etc., complete complying with standard specifications and as directed. In foundation and basement | 230.03 | M3 | 12500.45 | 2875478.5135 | 0 | 230.03 | 2875478.5135 |  | M3 | 0 | 154
1.31 | In ground floor Upto 4.50M height above basement. | 81.88 | M3 | 12668.25 | 1037276.31 | 0 | 81.88 | 1037276.31 |  | M3 | 0 | 72
1.32 | Above 4.50M height from basement | 64.19 | M3 | 12998.75 | 834389.7625 | 0 | 64.19 | 834389.7625 |  | M3 | 0 | 69
1.33 | Supplying and filling in foundation, basement, etc., with filling crushed stone sand in layers of not more than 15cm thick well watered, rammed and consolidated etc., complete complying with standard specification and as directed by the departmental officers. | 15.014 | M3 | 3455.65 | 51883.1291 | 0 | 0 | 0 | 15.014 | M3 | 51883.1291 | 16
1.34 | Cement Concrete 1:2:4 ( one cement, two sand, four aggregate) using 20mm of hard broken granite stone for all RCC works using machine for mixing concrete excluding cost of centering, Strutting, shuttering, and fabrication of reinforcement and placing the grills in position etc., but including finishing and curing etc., complete complying with standard specifications and as directed. In foundation basement | 7.142 | M3 | 11812.25 | 84363.0895 | 0 | 0 | 0 | 7.142 | M3 | 84363.0895 | 6
1.35 | In ground floor upto 4.50M height above basement | 7.95 | M3 | 11980 | 95241 | 0 | 0 | 0 | 7.95 | M3 | 95241 | 5
1.36 | Supplying and fixing in position of rain beating RCC Jolly, 5 cm thick in cement concrete 1:2:4 using 20mm stone jelly, including cost and conveyance of all materials labour charges for mixing, laying, casting, curing and fixing in position of jolly as directed and cost of mould, fabrication of reinforcement, etc., complete. | 0 | M2 | 1514.45 | 0 | 0 | 0 | 0 |  | M2 | 0 | 3
1.37 | Supplying and fixing of UPVC ventilator (Up-plasticized poly vinyl choloride) louvered ventilators of form profile size outer frame 60x58 mm and shutter profile size 60 x78mm both profiles reinforced with GI 1mm 125 GSM and 100% corrosion free multi colored chamber section with wall thick of 2mm. The EPDM rubber (Black colour ) covered with all the edges frame shutters. The corners and joints to be welded and cleaned. Radiation pin headed glass 4mm thick should be provided to the louvers. The Ventilator should be fixed to the wall with 100% packing with screws silicon packing round the frames. The Ventilator should got approved from Executive Engineer. | 0 | M2 | 8106 | 0 | 0 | 0 | 0 |  | M2 | 0 | 1.2
1.38 | Supplying and fixing M.S Grill to special windows and ventilators etc using 20mmx6mm angle including cost of MS grill, one of red oxide and fixing in position etc. complete complying with Standard Specification and as directed. | 0 | KG | 114.95 | 0 | 0 | 0 | 0 |  | KG | 0 | 100
1.39 | Fabricating, supplying and fixing in position of SOLID PVC DOORS with frames of sizes as per the specifications given below: PVC door frames made out of best quality PVC extruded section of 40mm * 58 mm * 2.50 mm +/- 0.3 mm thick, having multi chamber cross section and duly reinforced with steel to be mitre cut at the corners and welded including providing tie rod at the bottom and necessary weather seal etc., and PVC door shutters made out of extruded plastic section of 60 mm * 24 mm size in the configuration of an “A” section for shutter frames and multi-chamber hollow plastic section of 200 mm 200 mm1 mm (average thickness) with tongue and groove section for panels etc., with necessary holdfasts, rubber beedings, furniture fittings, locking | 0 | NOS | 3325 | 0 | 0 | 0 | 0 |  | NOS | 0 | 5
1.4 | Supplying and fixing in position Indian Water Closet (Oriya type) of size 580 x 440mm white glazed earthern ware of approved quality and brand with "P" or "S" trap conforming to BIS with sand cushion and forming flooring alround the closet using 40mm broken brick jelly in lime concrete 1:2:5 (One lime, Two sand and Five brick jelly) 100mm thick and finishing the top to the required slope and including giving necessary connection to PVC pipes (including the cost of 110mm dia CI pipe for a length of 600mm) by dismantling brick masonry wall / reinforced cement concrete roof / floor slab and making good the dismantled portion to the original condition with leakages etc., complete complying with standard specifications and as | 0 | NOS | 7546.3 | 0 | 0 | 0 | 0 |  | NOS | 0 | 3
1.41 | Paving the flooring with Ceramic tiles of size 305x305x6mm of approved quality and colour over a base layer of C.M.1:3, 20mm thick in all floors used 0.20 kg / m2 including finishing the joints and pointing flush with even surfaces etc., complete complying with standard specifications and as directed.. (The tiles should be got approved by the Executive engineer before use on works). | 0 | M2 | 1191.7 | 0 | 0 | 0 | 0 |  | M2 | 0 | 16
1.42 | Dadooing the walls with glazed tiles of size 305mmx200mmx6mm of approved quality and colour over a base layer of C.M.1:2, 10mm and pointing the joints with white cement mixed with colouring pigment at the rate of 0.40 kg/sq.m neatly in all floors, curing etc., complete complying with standard specification and as directed by the departmental officers. (The tiles should be got approved by the Executive engineer before use on works). | 0 | M2 | 1401 | 0 | 0 | 0 | 0 |  | M2 | 0 | 65
1.43 | Weathering course in brick jelly lime concrete using broken brick jelly of size 20mm uniform gauge in pure slaked lime (no sand to be used) to the proportion of brick jelly to lime being 32:12.5 by volume and laid over the RCC roof slab in a single layer of required slope and finished by beating the concrete with wooden beaters of approved pattern, keeping the surface constantly wet by sprinkling lime jaggery water, etc., complete as per standard specification and as directed by the departmental officers. | 0 | M3 | 6904.1 | 0 | 0 | 0 | 0 |  | M3 | 0 | 1.5
1.44 | Finishing the top of roof with one course of machine pressed tiles of size 23x23x2cm laid in cement mortar 1:2 (one of cement and two of sand)mixing with water proofing compound confirming to ISS at 2% weight of cement used and pointed with water proofing compound mixed with red oxide etc., complete complying with standard specification and as directed by the departmental officers. | 0 | M2 | 1562.75 | 0 | 0 | 0 | 0 |  | M2 | 0 | 21
1.45 | Painting new iron work with two coats of synthetic enamel paint of approved quality and colour over one coat of primer in all floors. The rate is inclusive of cost of all materials, labour charges, brushes and scaffolding charges etc. complete complying with standard specifications. (The paint should be got approved by Executive Engineer before use on works) | 0 | M2 | 174.65 | 0 | 0 | 0 | 0 |  | M2 | 0 | 10
1.46 | Supply and fixing in position of best Indian make white / colour glazed eartherware lipped mouth flat back urinal of best quality and approved make of size 430mmx260mmx350mm with GI Pipe, 32mm dia bell mouth PVC Connection and waste pipe, 15mm dia GI Pipe of required length, 15mm dia GM Wheel valve, 15mm dia brass nipple 2 Nos and fixing the urinals in position with necessary TW plugs, Clamps, Screws etc., including dismantling masonry and redoing the same to the original condition, etc., including painting the pipe with two coats of best quality approved synthetic enamel paint over one coat of red oxide primer and checked without any leakage etc., complete complying with standard specifications and as | 0 | NOS | 2903 | 0 | 0 | 0 | 0 |  | NOS | 0 | 2
1.47 | Supplying and fixing Brass Chromium platted Towel Rail 600mm Long and 20mm diameter with brackets of same materials including cost of teak wood plugs, CP Screws etc., complete complying with standard specification as directed by departmental officers. | 0 | NOS | 837 | 0 | 0 | 0 | 0 |  | NOS | 0 | 4
1.48 | Construction of Manhole chamber of size 600mx600mm to a total height of 800mm ie., 200mm above ground level and 600mm below ground level with base concrete of C.C 1:5:10 of 100mm thick over a sand cushion of 100mm thick the chamber should be constructed in brick masonry of 230mm thick in cement mortar with chamber burnt bricks of size 9”x4 3/8” x2 ¾” the inner sides of chamber is plastered with cement mortar 1;3 20mm thick outer chamber to a depth of 300mm plastered with cement mortar 1:5 12mm thick, chamber is covered with SRF covere slab 100mm thick the rate including cost of all materials, labour charges etc., complete complying with standard specification and as directed by the departmental officers. | 0 | NOS | 6352 | 0 | 0 | 0 | 0 |  | NOS | 0 | 4
1.49 | Supplying, and fixing PVC pipes of of 32mm dia of approved quality and variety conforming to pressure IS 4985. The rate is inclusive of cost of pipe, all taxes, conveyance charges of materials and all other labour charges for fixing the PVC pipe as directed by the departmental officers etc., complete complying with standard specifications. The PVC pipe should be got approved by the departmental officers before use on work. | 0 | RM | 350.8 | 0 | 0 | 0 | 0 |  | RM | 0 | 50
1.5 | Supplying, and fixing PVC pipes of 25mm dia of approved quality and variety conforming to pressure IS 4985. The rate is inclusive of cost of pipe, all taxes, conveyance charges of materials and all other labour charges for fixing the PVC pipe as directed by the departmental officers etc., complete complying with standard specifications. The PVC pipe should be got approved by the departmental officers before use on work | 0 | RM | 238.8 | 0 | 0 | 0 | 0 |  | RM | 0 | 25
1.51 | Supplying, and fixing PVC pipes of 110mm dia of approved quality and variety conforming to pressure IS 4985. The rate is inclusive of cost of pipe, all taxes, conveyance charges of materials and all other labour charges for fixing the PVC pipe as directed by the departmental officers etc., complete complying with standard specifications. The PVC pipe should be got approved by the departmental officers before use on work. | 0 | RM | 552 | 0 | 0 | 0 | 0 |  | RM | 0 | 20
1.52 | Supplying and fixing in position of best Indian make PVC Water Tank of 1000 litres capacity confirming to ISI standards as directed by the departmental officers including cost of material and conveyance charges of material to work site etc., complete complying with standard specifications. | 0 | NOS | 10050 | 0 | 0 | 0 | 0 |  | NOS | 0 | 1
1.53 | Supply and fixing in position wash hand basin with new one fixing in position best quality approved make white glazed earthenware wash hand basin of size 550x400mm with a pair of cast iron brackets, including cost of 15mm dia metre brass chromium plated pillar tap, 32mm dia metre G.M wheel valve 15mm dia brass nipple 15mm dia nylon connection etc., including fixing the wash hand basin in the wall in position with pair of CI brackets with teak wood plugs and screws and giving necessary water supply connection and painting the brackets with two coats of paint over a primary coat of anticorrosive paint including testing for leakage etc., complete complying with standard specification. | 0 | NOS | 4636 | 0 | 0 | 0 | 0 |  | NOS | 0 | 2
1.54 | Supplying and fixing in position of best approved quality of rain water down fall pipe of size 110mm dia having a pressure of 4Kg/sq.cm including cost of PVC bents, PVC shoe, cast iron gratings of required diameter and special clamps, brass screws nails etc., and fixing of cast iron gratings at junction of parapet and the junction of roof slab including finishing neatly etc., complete complying with standard specification as directed by the departmental officers. | 0 | RM | 638.7 | 0 | 0 | 0 | 0 |  | RM | 0 | 5
1.55 | Supplying and fixing AC ventilating shaft of 110mm dia with 3 metre height including cost of of 110mm dia AC cylindrical cowl of best approved quality etc., complete complying with standard specification and as directed by the departmental officers. | 0 | RM | 859.7 | 0 | 0 | 0 | 0 |  | RM | 0 | 3.5
| Sub Total = |  |  |  | 33881045.877 |  |  | 27330085.2358 |  |  | 6550960.6412
| GST 18% = |  |  |  | 6098588.2579 |  |  | 4919415.3424 |  |  | 1179172.9154
| Grand Total = |  |  |  | 39979634.1349 |  |  | 32249500.5783 |  |  | 7730133.5566
CERTIFICATES
1 | Certified that the work is in Progress.
2 | Certified that there is no recovery due from the contractor
3 | Certified that the contractor has engaged the Technical Assistant for supervising the work during execution.
4 | Certified that the contractor has utilized the cement,steel, of required quantity of good quality to this work.
| Asst Engineer |  |  | Asst. Exe. Engineer | [5 empty] | Exe. Engineer
| TNCSC Coimbatore |  |  | TNCSC Coimbatore | [5 empty] | TNCSC Chennai

## Set
Name of Work :Construction of New Taluk operational godown of 2500M.T(1X1500MT, 1X1000MT) capacity in TNCSC campus at Survey No.2347/1 to an extent of 1.21.44 Hectare at Nelliyalam Village in Pandalur Taluk in Nilgiris District.
| LS Ist & Part Bill |  | Date of Agt: | 2024-02-22
| Estimate Amount : 450 Lakhs |  | Agt Period: | 12 Months
| C.E(R) No. 74 /2023-2024 |  | DOC :
| AGT.No: 362/2023-2024 |  | DOC :
Set No | Description | M.Book Page | AE | AEE

## Pandalur Dt Wise
Pandalur |  | RA - 03 Details
S.no | Description | No |  |  | L | B | D | Qty | Unit
1
1.07 | Cemet Concrete 1:5: 10 (one cement, five sand, ten aggregate) using 40mm gauge HBG stone jelly including cost of all materials and labour charges etc., complete.
1500MT
| Basement flooring Down Side | 1 | X | 1 | 31.5 | 14.25 | 0.15 | 67.33 |  | 73.63
| Total | [6 empty] | 67.33 | M3
1.02 | Earth work excavation for foundation in all classes of soils and sub-soils and to full depth as may be directed except in hard rock requiring blasting including initial leads and lifts and refilling the sides of foundation with excavated earth in 150 mm layers well watered, rammed and consolidated including depositing surplus earth within the godown or inside compound in places shown with initial lead of 10 mts and initial lift of 2 mts. clearing, levelling the site, shoring, strutting, bailing of water wherever necessary etc., complete complying with standard specificationand as directed.
Septictank
| Septictank | 1 | X | 1 | 3.2 | 1.8 | 2.4 | 13.83
Toilet
| Column | 1 | X | 6 | 1.2 | 1.2 | 1.5 | 12.96
[8 empty] | 26.79 | cum
1.33 | Supplying and filling in foundation and basement with clean M-sand in layers not exceeding 150mm well watered rammed and consolidated including watering etc., complete complying with standard specification.
Septictank
| Septictank | 1 | X | 1 | 3.5 | 1.8 | 0.15 | 0.95
Toilet
| Column Footing | 1 | X | 6 | 1.2 | 1.2 | 0.1 | 0.864
[8 empty] | 1.814 | Cum
2
1.18 | Providing vacum de wattered controled cement concrte surfacing 100mm thick in required slope and chamber confirming M20 Grade with 20mm size stone aggregate castinsitu, smooth finish and levelling with double framed screed vibrator, excess water to be removed through vacum pump with bottom and top filter mat duly sealing the edges all round including provision of polythene sheet below the concerte layer before placing of concrete and finishing with power floated and power trowler to obtain the hard surface including provision of expansion joints at 6mtr intervels across the platform by cutting 6mm wide and full depth of concrete by contractos etc.,
1000MT
| Flooring | 1 | X | 1 | 42 | 14.25 | - | 598.5
| At Rolling shutter portion | 1 | X | 4 | 1.8 | 0.34 | - | 2.448
| Total | [6 empty] | 600.948 | M2
1500MT U/S
| Flooring | 1 | X | 1 | 31.5 | 14.25 | - | 448.875
| At Rolling shutter portion | 1 | X | 4 | 1.8 | 0.34 | - | 2.448
| Total | [6 empty] | 451.323 | M2
1500MT D/S
| Flooring | 1 | X | 1 | 31.5 | 14.25 | - | 448.875
| At Rolling shutter portion | 1 | X | 4 | 1.8 | 0.34 | - | 2.448
| Total | [6 empty] | 451.323 | M2
| Grand Total | [6 empty] | 1503.594 | M2
1.07 | CEMENT CONCRETE 1:5:10(one cement , five sand and ten aggregate)using 40mm gauge hard broken granite stone jelly for foundation including de-watering side shuttering , strutting, wherever necessary including curing etc., complete complying with standard specifications and as directed.
Septictank
| Septictank | 1 | X | 1 | 3.5 | 1.8 | 0.15 | 0.95
Toilet
| Column Footing | 1 | X | 6 | 1.2 | 1.2 | 0.15 | 1.3
[8 empty] | 2.25 | Cum
1.14 | Supplying, fabricating and placing in position MS/RTS grills for reinforcement for all R.C.C. works including cost of steel, labour for straightening, bending, cranking, tying grills with 18 gauge galvanized binding wire and placing grills in position complete complying with standard specification and as directed.
Steel Reinforcement for Toilet Footing and Column
Qtl
3
1.19 | Plastering with Cement mortor 1:5 (one cement,five sand) with 12 mm thick including cost of all materials,labour charges for finishing and curring etc., complete
INNER SIDE
1500MT
| Both side panel wall | 1 | X | 2 | 63 | - | 6.45 | 812.7
| Deduct for Rolling shutter | -2 | X | 4 | 1.8 | - | 2.6 | -37.44
| Deduct for Air inlet window | -2 | X | 11 | 0.6 | - | 0.6 | -7.92
| Deduct for ventilator | -2 | X | 28 | 1.2 | - | 0.6 | -40.32
| Add AI window sides | 11 | X | 2 | 2.4 | 0.23 | - | 12.14
| Add ventilator sides | 28 | X | 2 | 3.6 | 0.15 | - | 30.24
| Add sides of curtain portion | 4 | X | 3 | 0.26 | - | 0.45 | 1.4
| Bottom of Lintel @ R.Shutter | 2 | X | 4 | 2.1 | 0.26 | - | 4.37
| Bottom of curtain portion | 4 | X | 4 | 0.34 | 0.15 | - | 0.82
| Side of rolling shutter border | 4 | X | 4 | 0.22 | - | 2.6 | 9.15
| Both side Gable wall | 1 | X | 2 | 14.25 | - | 6.45 | 183.83
| Gable wall triangular portion | 2 X 1/2 |  |  | 14.25 | - | 2.4 | 68.4
| Basement panelwall bothside | 1 | X | 2 | 63 | - | 1.6 | 201.6
| Basement gablewall bothside | 1 | X | 2 | 14.25 | - | 1.6 | 45.6
| Deduct for Panel Column | -2 | X | 13 | 0.3 | - | 6 | -46.8
| Deduct for cable Column | -2 | X | 2 | 0.45 | - | 6 | -10.8
| Deduct for Lintel beam | -1 | X | 1 | 154.5 | - | 0.45 | -69.53
| Deduct for middle tie beam | -1 | X | 1 | 154.5 | - | 0.2 | -30.9
| Deduct for top tie beam | -1 | X | 1 | 154.5 | - | 0.45 | -69.53
| Total | [6 empty] | 1057.01
OUTER SIDE- Above basement
1500MT
| Both side panel wall | 1 | X | 2 | 63.46 | - | 6.45 | 818.63
| Deduct for Rolling shutter | -2 | X | 4 | 1.8 | - | 2.6 | -37.44
| Deduct for Air inlet window | -2 | X | 11 | 0.6 | - | 0.6 | -7.92
| Deduct for ventilator | -2 | X | 28 | 1.2 | - | 0.6 | -40.32
| Add ventilator sides | 28 | X | 2 | 3.6 | 0.08 | - | 16.13
| Add top of curtain Bend | 2 | X | 4 | 2.03 | 0.15 | - | 2.44
| Add inner side of border R.Shutter | 2 | X | 4 | 0.34 | - | 2.6 | 7.07
| Bottom of curtain bend | 2 | X | 4 | 1.8 | 0.19 | - | 2.74
| Add outside of border R.Shutter | 2 | X | 4 | 0.23 | - | 2.7 | 4.97
| D/f column | -2 | X | 15 | 0.3 | - | 6 | -54
| D/f Gable column | -2 | X | 2 | 0.23 | - | 6 | -5.52
| Add AI window border | 11 | X | 2 | 2.88 | 0.12 | - | 7.6
| Both side Gable wall Outer side Above basement | 1 | X | 2 | 15.15 | - | 0.45 | 13.64
| Gable wall triangular portion | 2 X 1/2 |  |  | 15.15 | - | 2.7 | 81.82
| Deduct for Lintel beam | -1 | X | 1 | 156.34 | - | 0.45 | -70.35
| Deduct for middle tie beam | -1 | X | 1 | 156.34 | - | 0.2 | -31.27
| Deduct for top tie beam | -1 | X | 1 | 156.34 | - | 0.45 | -70.35
| Basement outer | 1 | X | 1 | 156.34 | - | 1.7 | 265.78
| Total | [6 empty] | 904
| TOTAL PLASTERING AREA | 1057.01 |  |  | + | 904 | = | 1961.01 | M2
1.34 | Cement Concrete 1:2:4 ( one cement, two Msand, four aggregate) using 20mm of hard broken granite stone for all RCC works using machine for mixing concrete excluding cost of centering, Strutting, shuttering, but including laying, vibrating, with mechanical vibratos, finishing, curing etc, and providing fixtures like fan clamps in the RCC floor / roof slabs wherever necessary and bearing surface of walls, beams etc., shall be finished smooth with cement mortr 1:3 (one cement and three sand) and Kraft paper laid over it without claiming extra, etc.,complete complying with standard specifications and as directed by the departmental officers.
| Toilet Column mat 1st footing | 1 | X | 6 | 1.2 | 1.2 | 0.2 | 1.73
[8 empty] | 1.73 | cum
1.09 | BRICK WORK in cement mortor 1:5 (one cement, five Msand) using best quality second class chamber burnt bricks/ Fly ash bricks of size 9"x4 3/8"x2 3/4"for walls including cost of scaffolding curing, finishing etc.,complete complying with standard specifications and as directed.
Septictank
| Brickwork upto Cover Slab | 1 | X | 1 | 9.68 | 0.23 | 2.55 | 5.68
| Partion wall | 1 | X | 1 | 1.34 | 0.12 | 2.1 | 0.34
[8 empty] | 6.02 | cum
4
1.2 | PLASTERING with the RCC surface C.M.1:3 (one cement and three sand) 10mm thick including scaffolding,finishing,curing etc., complying with standard specification and as directed.
1500MT
| panel column | 2 | X | 15 | 0.76 | - | 7.9 | 180.12
| Gable column | 2 | X | 2 | 0.23 | - | 7.9 | 7.27
| Rat guard slab in panel wall bottom | 1 | X | 2 | 64.15 | 0.3 | - | 38.49
| Face of R.G Slab | 1 | X | 2 | 64.15 | - | 0.05 | 6.42
| Deduct for loading platform Face | -2 | X | 4 | 5.85 | - | 0.05 | -2.34
| Top of R.G Slab | 1 | X | 2 | 64.15 | 0.33 | - | 42.34
| Deduct for loading platform | -2 | X | 4 | 5.85 | 0.3 | - | -14.04
| Lintel beam alround | 1 | X | 2 | 155.89 |  | 0.45 | 140.3
| Middle tie beam alround | 1 | X | 2 | 155.89 |  | 0.2 | 62.36
| Top tie beam alround | 1 | X | 2 | 155.89 |  | 0.45 | 140.3
| Add for loading platform Top & bottom | 4 | X | 3 | 5.35 |  | 0.95 | 121.98
| Gable wall R.G. slab Top & bottom | 1 | X | 4 | 15.15 | 0.3 | - | 18.18
| Face of R.G Slab | 1 | X | 2 | 15.15 | - | 0.05 | 1.52
| Top and inner side of binder wall | 2 | X | 2 | 7.8 | 0.79 | - | 24.65
| Plinth beam alround | 1 | X | 2 | 155.89 |  | 0.3 | 93.53
| Add End sides | 2 | X | 2 | 0.34 | - | 0.45 | 0.61
| Total | [6 empty] | 861.69 | M2
1.12 | Supplying and erecting steel centering including necessary supports for planesurfaces for Reinforced Cement Concrete works such as column footing, column pedestals, plinth beams, grade beams, staircase steps etc., which require only nominal strutting using Mild Steel sheets of size 90 x 60 cm and 10 BG stiffened with welded Mild Steel angle of size 25mm x 25mm x 3 mm for boarding laid over silver oak joists of size 10cm x 6.50 cm spaced at not more than 75 cm centre to centre etc., complete complying with the standard specification. (payment for centering shall be given after the For Plinth beam grade beam, etc.,
| Column 2nd footing | 1 | X | 6 | 3.6 | - | 0.2 | 4.32
[8 empty] | 4.32 | Sqm
1.34 | Cement Concrete 1:2:4 ( one cement, two Msand, four aggregate) using 20mm of hard broken granite stone for all RCC works using machine for mixing concrete excluding cost of centering, Strutting, shuttering, but including laying, vibrating, with mechanical vibratos, finishing, curing etc, and providing fixtures like fan clamps in the RCC floor / roof slabs wherever necessary and bearing surface of walls, beams etc., shall be finished smooth with cement mortr 1:3 (one cement and three sand) and Kraft paper laid over it without claiming extra, etc.,complete complying with standard specifications and as directed by the departmental officers.
| Column mat 2nd footing | 1 | X | 6 | 0.9 | 0.9 | 0.2 | 0.972
[8 empty] | 0.972 | cum
5
1.21 | Painting two coats of newly platered wall surface with ready mixed plastic emulsion paint of first class quality and of approved colour over a priming coat including thorough scrapping clean removal of dirt, and including plater of paris
1500MT Outer
| Plastering cm 1: 5 | [6 empty] | 904
| Plastering cm 1:3 | [6 empty] | 861.69
| Total | [6 empty] | 1765.69
1000MT Outer
| Plastering cm 1: 5 | [6 empty] | 735.1
| Plastering cm 1:3 | [6 empty] | 539.8
| Total | [6 empty] | 1274.9
| Grand Total | [6 empty] | 3040.59 | M2
1.26 | Supplying and fixing corrugated Poly Carbonate Sheet of size 3 mx1.06m of 3mm tk on the roof in-between the colour coated Galvolume sheets for proper lighting with necessary screws and EPDM rubber washers, Complying with standard specification and as directed and specified by the departmental officers including cost of loading ,unloading and transportation charges etc complete .,
1000MT
| Roofing | 1 | X | 4 | 3 | 1 | - | 12
1500MT
| Roofing | 1 | X | 7 | 3 | 1 | - | 21
| Total | [6 empty] | 33 | M2
1.12 | Supplying and erecting steel centering including necessary supports for planesurfaces for Reinforced Cement Concrete works such as column footing, column pedestals, plinth beams, grade beams, staircase steps etc., which require only nominal strutting using Mild Steel sheets of size 90 x 60 cm and 10 BG stiffened with welded Mild Steel angle of size 25mm x 25mm x 3 mm for boarding laid over silver oak joists of size 10cm x 6.50 cm spaced at not more than 75 cm centre to centre etc., complete complying with the standard specification. (payment for centering shall be given after the For Plinth beam grade beam, etc.,
| Toilet Column Upto Plinthbeam | 1 | X | 6 | 0.92 |  | 0.72 | 3.98
[8 empty] | 3.98 | Sqm
1.34 | Cement Concrete 1:2:4 ( one cement, two Msand, four aggregate) using 20mm of hard broken granite stone for all RCC works using machine for mixing concrete excluding cost of centering, Strutting, shuttering, but including laying, vibrating, with mechanical vibratos, finishing, curing etc, and providing fixtures like fan clamps in the RCC floor / roof slabs wherever necessary and bearing surface of walls, beams etc., shall be finished smooth with cement mortr 1:3 (one cement and three sand) and Kraft paper laid over it without claiming extra, etc.,complete complying with standard specifications and as directed by the departmental officers.
| Toilet Column Upto Plinthbeam | 1 | X | 6 | 0.23 | 0.23 | 0.72 | 0.23
[8 empty] | 0.23 | cum
1.12 | Supplying and erecting steel centering including necessary supports for planesurfaces for Reinforced Cement Concrete works such as column footing, column pedestals, plinth beams, grade beams, staircase steps etc., which require only nominal strutting using Mild Steel sheets of size 90 x 60 cm and 10 BG stiffened with welded Mild Steel angle of size 25mm x 25mm x 3 mm for boarding laid over silver oak joists of size 10cm x 6.50 cm spaced at not more than 75 cm centre to centre etc., complete complying with the standard specification. (payment for centering shall be given after the For Plinth beam grade beam, etc.,
| Septictank Cover Slab | 1 | X | 1 | 3.04 | 1.34 |  | 4.08
| Sides | 1 | X | 1 | 10.6 |  | 0.15 | 1.59
| D/f for Manhole | -1 | X | 1 | 0.6 | 0.6 |  | -0.36
[8 empty] | 5.31 | Sqm
1.14 | Supplying, fabricating and placing in position MS/RTS grills for reinforcement for all R.C.C. works including cost of steel, labour for straightening, bending, cranking, tying grills with 18 gauge galvanized binding wire and placing grills in position complete complying with standard specification and as directed.
| Steel Reinforcement for Cover slab | [6 empty] | 0
[8 empty] | 0 | Qtl
6
1.27 | Painting the walls with two coats of oil bound distemper over one coat of water based cement primer including cost of distemper, primer, cleaning, scrabbing the walls, rendering the walls smooth with necessary putty, brushes, scaffolding arrangements, labour charges etc., complete, complying standard specification and as directed. ( The quality and colour of oil bound distemper should got approved by the Executive Engineer before use.)
| 1500MT Inner | [6 empty] | 1057.01
| 1000MT Inner | [6 empty] | 745.3
| Total | [6 empty] | 1802.31 | M2
1.28 | Supply and fixing of 40x6mm G.I flat over the Galvalume sheet roofing which is placed on the top of purlin in the longitutinol direction to avoid the lifting of roofing due to wind, the rate inclusive of neccesary G.I screw, Rubber, Aluminium whaser with necessary adhesive flashing tap fixed directly over the galvalume sheet, labour charges for fixing, conveyance loading, unloading and cutting, etc. complete | [9 empty] | 288
1000MT
| Roofing | 2 | X | 4 | 42 |  | - | 336
1500MT
| Roofing | 2 | X | 4 | 63 |  | - | 504
| Total | [6 empty] | 840 | Rm
1.23 | Supplying and fixing of Rotary Ventilators over the roof with necessary bolt and nut arrangement to withstand the wind velocity as specified by the departmental officers. (Size 600mm x 600mm)
1000MT
| Roofing | 1 | X | 4 |  |  | - | 4
1500MT
| Roofing | 1 | X | 7 |  |  | - | 7
| Total | [6 empty] | 11 | Nos
1.02 | Earth work excavation for foundation in all classes of soils and sub-soils and to full depth as may be directed except in hard rock requiring blasting including initial leads and lifts and refilling the sides of foundation with excavated earth in 150 mm layers well watered, rammed and consolidated including depositing surplus earth within the godown or inside compound in places shown with initial lead of 10 mts and initial lift of 2 mts. clearing, levelling the site, shoring, strutting, bailing of water wherever necessary etc., complete complying with standard specificationand as directed.
| Grade Beam | 1 | X | 1 | 17.72 | 0.45 | 0.6 | 4.79
| Cross Wall (Long) | 1 | X | 1 | 4.98 | 0.45 | 0.6 | 1.35
| Cross Wall (Short) | 1 | X | 1 | 2.98 | 0.45 | 0.6 | 0.81
[8 empty] | 6.95 | cum
1.33 | Supplying and filling in foundation and basement with clean M-sand in layers not exceeding 150mm well watered rammed and consolidated including watering etc., complete complying with standard specification.
| Grade Beam | 1 | X | 1 | 17.72 | 0.45 | 0.15 | 1.2
| Cross Wall (Long) | 1 | X | 1 | 4.98 | 0.45 | 0.15 | 0.34
| Cross Wall (Short) | 1 | X | 1 | 2.98 | 0.45 | 0.15 | 0.21
[8 empty] | 1.75 | cum
7
1.07 | CEMENT CONCRETE 1:5:10(one cement , five sand and ten aggregate)using 40mm gauge hard broken granite stone jelly for foundation including de-watering side shuttering , strutting, wherever necessary including curing etc., complete complying with standard specifications and as directed.
| Toilet | [6 empty] | 0
| Grade Beam | 1 | X | 1 | 17.72 | 0.45 | 0.15 | 1.2
| Cross Wall (Long) | 1 | X | 1 | 4.98 | 0.45 | 0.15 | 0.34
| Cross Wall (Short) | 1 | X | 1 | 2.98 | 0.45 | 0.15 | 0.21
[8 empty] | 1.75 | cum
1.14 | Supplying, fabricating and placing in position MS/RTS grills for reinforcement for all R.C.C. works including cost of steel, labour for straightening, bending, cranking, tying grills with 18 gauge galvanized binding wire and placing grills in position complete complying with standard specification and as directed.
| For Toilet Plinthbeam | [6 empty] | 0
| For Road | [6 empty] | 0
[8 empty] | 0 | Qtl
8
1.12 | Supplying and erecting steel centering including necessary supports for planesurfaces for Reinforced Cement Concrete works such as column footing, column pedestals, plinth beams, grade beams, staircase steps etc., which require only nominal strutting using Mild Steel sheets of size 90 x 60 cm and 10 BG stiffened with welded Mild Steel angle of size 25mm x 25mm x 3 mm for boarding laid over silver oak joists of size 10cm x 6.50 cm spaced at not more than 75 cm centre to centre etc., complete complying with the standard specification. (payment for centering shall be given after the For Plinth beam grade beam, etc.,
Grade beam for Toilet Plinth Beam
| Allround | 1 | X | 2 | 17.72 |  | 0.23 | 8.16
| Longitutional wall | 1 | X | 2 | 5.2 |  | 0.23 | 2.4
| Cross wall | 1 | X | 2 | 3.2 |  | 0.23 | 1.48
[8 empty] | 12.04 | Sqm
1.34 | Cement Concrete 1:2:4 ( one cement, two Msand, four aggregate) using 20mm of hard broken granite stone for all RCC works using machine for mixing concrete excluding cost of centering, Strutting, shuttering, but including laying, vibrating, with mechanical vibratos, finishing, curing etc, and providing fixtures like fan clamps in the RCC floor / roof slabs wherever necessary and bearing surface of walls, beams etc., shall be finished smooth with cement mortr 1:3 (one cement and three sand) and Kraft paper laid over it without claiming extra, etc.,complete complying with standard specifications and as directed by the departmental officers.
Toilet Grade beam
| Allround | 1 | X | 1 | 17.72 | 0.23 | 0.23 | 0.94
| Longitutional wall | 1 | X | 1 | 5.2 | 0.23 | 0.23 | 0.28
| Cross wall | 1 | X | 1 | 3.2 | 0.23 | 0.23 | 0.17
| Septictank | [6 empty] | 0
| Cover Slab | 1 | X | 1 | 3.5 | 1.8 | 0.12 | 0.76
| D/f for Manhole | -1 | X | 1 | 0.6 | 0.6 | 0.12 | -0.05
| Total | [6 empty] | 2.1 | Cum
9
1.12 | Supplying and erecting steel centering including necessary supports for planesurfaces for Reinforced Cement Concrete works such as column footing, column pedestals, plinth beams, grade beams, staircase steps etc., which require only nominal strutting using Mild Steel sheets of size 90 x 60 cm and 10 BG stiffened with welded Mild Steel angle of size 25mm x 25mm x 3 mm for boarding laid over silver oak joists of size 10cm x 6.50 cm spaced at not more than 75 cm centre to centre etc., complete complying with the standard specification. (payment for centering shall be given after the For Plinth beam grade beam, etc.,
Toilet
| Column Plinthbeam to Roof | 1 | X | 6 | 0.92 |  | 3.05 | 16.84
[8 empty] | 16.84 | Sqm
1.34 | Cement Concrete 1:2:4 ( one cement, two Msand, four aggregate) using 20mm of hard broken granite stone for all RCC works using machine for mixing concrete excluding cost of centering, Strutting, shuttering, but including laying, vibrating, with mechanical vibratos, finishing, curing etc, and providing fixtures like fan clamps in the RCC floor / roof slabs wherever necessary and bearing surface of walls, beams etc., shall be finished smooth with cement mortr 1:3 (one cement and three sand) and Kraft paper laid over it without claiming extra, etc.,complete complying with standard specifications and as directed by the departmental officers.
Toilet
| Column Plinthbeam to Roof | 1 | X | 6 | 0.23 | 0.23 | 3.05 | 0.97
[8 empty] | 0.97 | cum
10
1.09 | Brick work using country bricks of size 8”x3/4x4-1/4 x 2-3/4 in cement mortar 1:6 (one cement and six crushed stone M sand) including curing near finishing etc., complete complying with standard specification. Ground floor upto 4.5m ht., below basement, above basement.
Toilet
Plinthbeam to FFL
| Allround | 1 | X | 1 | 17.72 | 0.23 | 0.75 | 3.06
| Longitutional wall | 1 | X | 1 | 5.2 | 0.23 | 0.75 | 0.9
| Cross wall | 1 | X | 3 | 2.13 | 0.23 | 0.75 | 1.11
[8 empty] | 5.07 | Cum
11
1.33 | Supplying and filling in foundation and basement with clean M-sand in layers not exceeding 150mm well watered rammed and consolidated including watering etc., complete complying with standard specification.
Toilet
| Basement | 1 | X | 4 | 1.21 | 2.13 | 0.75 | 7.74
| passage | 1 | X | 1 | 5.2 | 0.95 | 0.75 | 3.71
[8 empty] | 11.45 | cum
1.07 | CEMENT CONCRETE 1:5:10(one cement , five sand and ten aggregate)using 40mm gauge hard broken granite stone jelly for foundation including de-watering side shuttering , strutting, wherever necessary including curing etc., complete complying with standard specifications and as directed.
Toilet
| Basement | 1 | X | 4 | 1.21 | 2.13 | 0.15 | 1.55
| passage | 1 | X | 1 | 5.2 | 0.95 | 0.15 | 0.75
[8 empty] | 2.3 | cum
12
1.09 | Brick work using country bricks of size 8”x3/4x4-1/4 x 2-3/4 in cement mortar 1:6 (one cement and six crushed stone M sand) including curing near finishing etc., complete complying with standard specification. Ground floor upto 4.5m ht., below basement, above basement.
Toilet
FFL to Lintel
| Allround | 1 | X | 1 | 17.72 | 0.23 | 2.1 | 8.56
| Longitutional wall | 1 | X | 1 | 5.2 | 0.12 | 2.1 | 1.32
| Cross wall | 1 | X | 3 | 2.13 | 0.12 | 2.1 | 1.62
| D/f for Open | -1 | X | 1 | 0.9 | 0.23 | 2.1 | -0.44
| Toliet Door | -1 | X | 4 | 0.75 | 0.23 | 2.1 | -1.45
| Jally Open | -1 | X | 4 | 1.21 | 0.23 | 0.6 | -0.67
| vendilator | -1 | X | 4 | 0.6 | 0.23 | 0.45 | -0.25
| D/f Column Portion | -1 | X | 6 | 0.23 | 0.23 | 3.05 | -0.97
[8 empty] | 7.72 | Cum
13
1.14 | Supplying, fabricating and placing in position MS/RTS grills for reinforcement for all R.C.C. works including cost of steel, labour for straightening, bending, cranking, tying grills with 18 gauge galvanized binding wire and placing grills in position complete complying with standard specification and as directed.
Toilet
| Lintel Beam | [6 empty] | 0
[8 empty] | 0 | Qtl
1.12 | Supplying and erecting steel centering including necessary supports for planesurfaces for Reinforced Cement Concrete works such as column footing, column pedestals, plinth beams, grade beams, staircase steps etc., which require only nominal strutting using Mild Steel sheets of size 90 x 60 cm and 10 BG stiffened with welded Mild Steel angle of size 25mm x 25mm x 3 mm for boarding laid over silver oak joists of size 10cm x 6.50 cm spaced at not more than 75 cm centre to centre etc., complete complying with the standard specification. (payment for centering shall be given after the For Plinth beam grade beam, etc.,
Toilet
Lintel Beam
| Allround | 1 | X | 2 | 17.72 |  | 0.15 | 5.32
| Longitutional wall | 1 | X | 2 | 5.2 |  | 0.15 | 1.56
| Cross wall | 2 | X | 3 | 3.2 |  | 0.15 | 2.88
| Sunshade | 1 | X | 1 | 1.5 |  | 0.6 | 0.9
| Sides | 1 | X | 1 | 2.7 |  | 0.08 | 0.22
| Door Bttoms | 1 | X | 1 | 0.9 |  | 0.23 | 0.21
| Jally Bottom | 1 | X | 4 | 1.21 |  | 0.23 | 1.12
| Toilet Door Bottom | 1 | X | 4 | 0.75 |  | 0.23 | 0.69
| Vendilator | 1 | X | 4 | 0.6 |  | 0.23 | 0.56
[8 empty] | 13.46 | Sqm
1.34 | Cement Concrete 1:2:4 ( one cement, two Msand, four aggregate) using 20mm of hard broken granite stone for all RCC works using machine for mixing concrete excluding cost of centering, Strutting, shuttering, but including laying, vibrating, with mechanical vibratos, finishing, curing etc, and providing fixtures like fan clamps in the RCC floor / roof slabs wherever necessary and bearing surface of walls, beams etc., shall be finished smooth with cement mortr 1:3 (one cement and three sand) and Kraft paper laid over it without claiming extra, etc.,complete complying with standard specifications and as directed by the departmental officers.
Toilet
Lintel Beam
| Allround | 1 | X | 1 | 17.72 | 0.23 | 0.15 | 0.62
| Longitutional wall | 1 | X | 1 | 5.2 | 0.23 | 0.15 | 0.18
| Cross wall | 1 | X | 3 | 3.2 | 0.23 | 0.15 | 0.34
[8 empty] | 1.14 | Cum
14
1.09 | Brick work using country bricks of size 8”x3/4x4-1/4 x 2-3/4 in cement mortar 1:6 (one cement and six crushed stone M sand) including curing near finishing etc., complete complying with standard specification. Ground floor upto 4.5m ht., below basement, above basement.
Toilet
Lintel to Roof
| Allround | 1 | X | 1 | 17.72 | 0.23 | 1 | 4.08
| Longitutional wall | 1 | X | 1 | 5.2 | 0.12 | 1 | 0.63
| Cross wall | 1 | X | 3 | 2.13 | 0.12 | 1 | 0.77
[8 empty] | 5.48 | Cum
15
1.12 | Supplying and erecting steel centering including necessary supports for planesurfaces for Reinforced Cement Concrete works such as column footing, column pedestals, plinth beams, grade beams, staircase steps etc., which require only nominal strutting using Mild Steel sheets of size 90 x 60 cm and 10 BG stiffened with welded Mild Steel angle of size 25mm x 25mm x 3 mm for boarding laid over silver oak joists of size 10cm x 6.50 cm spaced at not more than 75 cm centre to centre etc., complete complying with the standard specification. (payment for centering shall be given after the For Plinth beam grade beam, etc.,
Toilet
| Roof Bottom | 1 | X | 1 | 5.66 |  | 3.66 | 20.72
| Sides | 1 | X | 1 | 18.64 |  | 0.12 | 2.24
| Beam Sides | [6 empty] | 0
| Allround | 1 | X | 2 | 17.72 |  | 0.23 | 8.16
| Longitutional wall | 1 | X | 2 | 5.2 |  | 0.23 | 2.4
| Cross wall | 2 | X | 3 | 2.13 |  | 0.23 | 2.94
[8 empty] | 36.46 | Sqm
1.14 | Supplying, fabricating and placing in position MS/RTS grills for reinforcement for all R.C.C. works including cost of steel, labour for straightening, bending, cranking, tying grills with 18 gauge galvanized binding wire and placing grills in position complete complying with standard specification and as directed.
Toilet
| Roof and Beam | [6 empty] | 0
[8 empty] | 0 | Qtl
1.35 | Cement Concrete 1:2:4 ( one cement, two Msand, four aggregate) using 20mm of hard broken granite stone for all RCC works using machine for mixing concrete excluding cost of centering, Strutting, shuttering, but including laying, vibrating, with mechanical vibratos, finishing, curing etc, and providing fixtures like fan clamps in the RCC floor / roof slabs wherever necessary and bearing surface of walls, beams etc., shall be finished smooth with cement mortr 1:3 (one cement and three sand) and Kraft paper laid over it without claiming extra, etc.,complete complying with standard specifications and as directed by the departmental officers.
Toilet
| Roof | 1 | X | 1 | 5.66 | 3.66 | 0.12 | 2.49
| Beams | [6 empty] | 0
| Allround | 1 | X | 1 | 17.72 | 0.23 | 0.23 | 0.94
| Longitutional wall | 1 | X | 1 | 5.2 | 0.23 | 0.23 | 0.28
| Cross wall | 1 | X | 3 | 2.13 | 0.23 | 0.23 | 0.34
| Godown No 1,2 | 1 | x | 2 | 4.5 | 1.5 | 0.15 | 2.03
| Rat Guard | 1 | x | 1 | 35 | 0.3 | 0.15 | 1.58
| Total | [6 empty] | 7.66 | Cum
16
1.12 | Supplying and erecting steel centering including necessary supports for planesurfaces for Reinforced Cement Concrete works such as column footing, column pedestals, plinth beams, grade beams, staircase steps etc., which require only nominal strutting using Mild Steel sheets of size 90 x 60 cm and 10 BG stiffened with welded Mild Steel angle of size 25mm x 25mm x 3 mm for boarding laid over silver oak joists of size 10cm x 6.50 cm spaced at not more than 75 cm centre to centre etc., complete complying with the standard specification. (payment for centering shall be given after the For Plinth beam grade beam, etc.,
| Toilet Parapetwall | 1 | X | 6 | 0.92 |  | 0.9 | 4.97
[8 empty] | 4.97 | Sqm
1.35 | Cement Concrete 1:2:4 ( one cement, two Msand, four aggregate) using 20mm of hard broken granite stone for all RCC works using machine for mixing concrete excluding cost of centering, Strutting, shuttering, but including laying, vibrating, with mechanical vibratos, finishing, curing etc, and providing fixtures like fan clamps in the RCC floor / roof slabs wherever necessary and bearing surface of walls, beams etc., shall be finished smooth with cement mortr 1:3 (one cement and three sand) and Kraft paper laid over it without claiming extra, etc.,complete complying with standard specifications and as directed by the departmental officers.
| Toilet Parapetwall | 1 | X | 6 | 0.23 | 0.23 | 0.9 | 0.29
[8 empty] | 0.29 | cum
17
1.09 | Brick work using country bricks of size 8”x3/4x4-1/4 x 2-3/4 in cement mortar 1:6 (one cement and six crushed stone M sand) including curing near finishing etc., complete complying with standard specification. Ground floor upto 4.5m ht., below basement, above basement.
Toilet
| Parapet Wall | 1 | X | 1 | 17.72 | 0.23 | 0.45 | 1.84
[8 empty] | 1.84 | Cum
2.08 | Special PLASTERING with cement mortor 1:3 (one cement and three sand) 10mm thick including cost of conveyance of all materials to site and including all labour charges etc complete.
| Toilet Ceiling | 1 |  | 4 | 1.21 | 2.13 |  | 10.31
| Passage ceiling | 1 |  | 1 | 5.2 | 0.9 |  | 4.68
| Sunshade Front side | 1 |  | 1 | 1.5 | 1.28 |  | 1.92
| Sunshade Front side (Sides) | 1 |  | 2 | 0.6 |  | 0.08 | 0.1
| For Septic Tank | [6 empty] | 0
| Septic Tank ceiling | 1 |  | 1 | 3.04 | 1.34 |  | 4.08
| Septic Tank Top | 1 |  | 1 | 3.5 | 1.8 |  | 6.3
| Septic Tank sides | 1 |  | 1 | 10.6 |  | 0.45 | 4.77
[8 empty] | 32.16 | Sqm
18
1.19 | PLASTERING with cement mortor 1:5 (one cement and five M sand) 12mm thick including cost and conveyance of all materials to site, loading and unloading charges and labour charges for mixing, laying and curing etc., complete complying with standard specification
Toilet
| Inner Toilet Alround | 1 | x | 4 | 6.68 |  | 3.05 | 81.5
| Deduction for door | 1 | x | 4 | 0.75 |  | 2.1 | 6.3
| Deduction Ventilator | 1 | x | 4 | 0.6 |  | 0.45 | 1.08
| Inner passage alround | 1 | x | 1 | 12.3 |  | 3.05 | 37.52
| Deduction door | 1 | x | 1 | 0.9 |  | 2.1 | 1.89 |  |  |  | 1
| Deduction for Jally | 1 | x | 4 | 1.2 |  | 0.6 | 2.88
| Door Jambs | 1 | x | 1 | 5.1 | 0.23 |  | 1.18
| Toilet Door Jambs | 1 | x | 4 | 4.95 | 0.23 |  | 4.56
| Jally Jambs | 1 | x | 4 | 3.6 | 0.23 |  | 3.32
| Ventilator Jambs | 1 | x | 4 | 0.54 | 0.23 |  | 0.5
| OUTER | [6 empty] | 0
| Alround | 1 | x | 1 | 18.64 |  | 4.52 | 84.26
| Deduction for door | 1 | x | 1 | 0.9 |  | 2.1 | 1.89
| Deduction for Jally | 1 | x | 4 | 1.2 |  | 0.6 | 2.88
| Deduction for Ventilator | 1 | x | 4 | 0.6 |  | 0.45 | 1.08
| D/F for Toilet steps | 1 | x | 1 | 1.5 |  | 1.2 | 1.8
| Add for parapet inner | 1 | x | 1 | 27.74 | 0.83 |  | 23.03
| Add for Toilet step thread | 1 | x | 5 | 1.5 | 0.23 |  | 1.73
| Add for Toilet step riser | 1 | x | 5 | 1.5 |  | 0.15 | 1.13
| Add for Toilet step sides | 1 | x | 2 | 0.92 |  | 0.9 | 1.66
| For Septic Tank | [6 empty] | 0
| Septic Tank inner alround | 1 | x | 1 | 8.76 |  | 2.55 | 22.34
| partition Wall | 1 | x | 2 | 1.34 |  | 2.1 | 5.63
| Total | [6 empty] | 288.16 | Sqm
19

## Steel 1000MT
Pandalur Steel - BBS RA02
S.no | Description | No's |  |  | Cutting Length | #8mm | #10mm | #12mm | #16mm | #20mm
Total Length
2
1.14 | PLINTH BEAM
PB 01
| #12mm main bar TOP & Bot | 2 | X | 6 | 33.68 |  |  | 404.16
| #12mm main bar Lap | 2 | X | 18 | 0.6 |  |  | 21.6
| #10mm Stirupps | 2 | X | 206 | 1.6 |  | 659.2
| #8mm distribution bar | 2 | X | 3 | 30.88 | 185.28
| #8mm distribution Lap bar | 2 | X | 9 | 0.4 | 7.2
PB 02 (Loading plot form)
| #16mm main bar Top&Bot | 2 | X | 12 | 7.45 |  |  |  | 178.8
| #12mm Stirupps | 2 | X | 118 | 2.23 |  |  | 526.28
| #12mm main bar | 2 | X | 118 | 1.3 |  |  | 306.8
| #12mm distribution Top | 2 | X | 22 | 5.35 |  |  | 235.4
| #12mm distribution Bot | 2 | X | 18 | 5.35 |  |  | 192.6
PB 01
| #12mm main bar Top&Bot | 3 | X | 6 | 15.4 |  |  | 277.2
| #12mm main bar Lap | 3 | X | 6 | 0.8 |  |  | 14.4
| #10mm Stirupps | 3 | X | 101 | 1.63 |  | 493.89
| #8mm distribution bar | 3 | X | 3 | 15.6 | 140.4
| #8mm distribution Lap | 3 | X | 3 | 0.4 | 3.6
[6 empty] | 336.48 | 1153.09 | 1978.44 | 178.8
3
Column upto Top Level
C1
| #16mm main bar | 10 | X | 4 | 3.6 |  |  |  | 144
| #12mm main bar | 10 | X | 6 | 3.6 |  |  | 216
| #8mm stirupps | 10 | X | 20 | 1.3 | 260
| #8mm stirupps | 10 | X | 40 | 1.04 | 416
[8 empty] | 0 | 0
| #16mm main bar | 6 | X | 4 | 4.6 |  |  |  | 110.4
| #12mm main bar | 6 | X | 6 | 4.6 |  |  | 165.6
| #8mm stirupps | 6 | X | 26 | 1.3 | 202.8
| #8mm stirupps | 6 | x | 42 | 1.04 | 262.08
| C2 |  |  |  |  | 0
| #16mm main bar | 2 | X | 4 | 3.6 | 28.8 |  |  | 28.8
| #12mm main bar | 2 | X | 4 | 3.6 |  |  | 28.8
| #8mm stirupps | 2 | X | 20 | 1.06 | 42.4
| #8mm stirupps | 2 | X | 20 | 0.82 | 32.8
0
| #16mm main bar | 2 | X | 4 | 4.6 |  |  |  | 36.8
| #12mm main bar | 2 | X | 4 | 4.6 |  |  | 36.8
| #8mm stirupps | 2 | X | 26 | 1.06 | 55.12
| #8mm stirupps | 2 | X | 42 | 0.82 | 68.88
C3
| #16mm main bar | 2 | X | 4 | 3.6 |  |  |  | 28.8
| #12mm main bar | 2 | X | 6 | 3.6 |  |  | 43.2
| #8mm stirupps | 2 | X | 20 | 1.26 | 50.4
| #8mm stirupps | 2 | X | 40 | 1.14 | 91.2
| #16mm main bar | 2 | X | 4 | 4.6 |  |  |  | 36.8
| #12mm main bar | 2 | X | 6 | 4.6 |  |  | 55.2
| #8mm stirupps | 2 | X | 26 | 1.26 | 65.52
| #8mm stirupps | 2 | X | 42 | 1.14 | 95.76
[6 empty] | 1671.76 | 0 | 545.6 | 385.6 | 0
5
GF Lintel Beam
| #20mm main bar Top&Bot | 2 | X | 6 | 42.98 |  |  |  |  | 515.76
| #20mm main bar Lap | 2 | X | 24 | 1 |  |  |  |  | 48
| #12mm main bar | 2 | X | 2 | 42.98 |  |  | 171.92
| #12mm main bar Lap | 2 | X | 8 | 0.6 |  |  | 9.6
| #8mm Stirupps | 2 | X | 280 | 1.26 | 705.6
| #20mm main bar Top&Bot | 2 | X | 6 | 15.4 |  |  |  |  | 184.8
| #20mm main bar Lap | 2 | X | 6 | 1 |  |  |  |  | 12
| #12mm main bar | 2 | X | 2 | 15.4 |  |  | 61.6
| #12mm main bar Lap | 2 | X | 2 | 0.66 |  |  | 2.64
| #8mm Stirupps | 2 | X | 101 | 1.26 | 254.52
Cut Lintel beam
| #12mm main bar Top&Bot | 14 | X | 4 | 1.1 |  |  | 61.6
| #8mm Stirupps | 14 | X | 8 | 0.85 | 95.2
| #12mm main bar | 14 | X | 6 | 0.75 |  |  | 63
| #8mm distribution bar | 14 | X | 1 | 1.1 | 15.4
Rolling Shutter Beam
| #12mm main bar | 4 | X | 16 | 1.33 |  |  | 85.12
| #8mm distribution bar | 4 | X | 7 | 2.4 | 67.2
Open lintel
| #16mm main bar | 2 | X | 4 | 2.4 |  |  |  | 19.2
| #8mm Stirupps | 2 | X | 16 | 0.8 | 25.6
[6 empty] | 1163.52 | 0 | 455.48 | 19.2 | 760.56
7
Top Tie Beam
| #20mm main bar Bot | 2 | X | 2 | 42.98 |  |  |  |  | 171.92
| #20mm main bar Lap | 2 | X | 8 | 1 |  |  |  |  | 16
| #16mm main bar Top&Bot | 2 | X | 4 | 42.98 |  |  |  | 343.84
| #16mm main bar Lap | 2 | X | 16 | 0.8 |  |  |  | 25.6
| #12mm main bar | 2 | X | 2 | 42.98 |  |  | 171.92
| #12mm main bar Lap | 2 | X | 8 | 0.6 |  |  | 9.6
| #8mm Stirupps | 2 | X | 281 | 1.26 | 708.12
| #20mm main bar Bot | 2 | X | 2 | 15.4 |  |  |  |  | 61.6
| #20mm main bar Lap | 2 | X | 8 | 1 |  |  |  |  | 16
| #16mm main bar Top&Bot | 2 | X | 4 | 15.4 |  |  |  | 123.2
| #16mm main bar Lap | 2 | X | 4 | 0.8 |  |  |  | 6.4
| #12mm main bar | 2 | X | 2 | 15.4 |  |  | 61.6
| #12mm main bar Lap | 2 | X | 2 | 0.6 |  |  | 2.4
| #8mm Stirupps | 2 | X | 101 | 1.26 | 254.52
[6 empty] | 962.64 | 0 | 245.52 | 499.04 | 265.52

## Steel 1500MT
Pandalur Steel - BBS RA02
S.no | Description | No's |  |  | Cutting Length | #8mm | #10mm | #12mm | #16mm | #20mm
Total Length
2
1.14 | PLINTH BEAM
PB 01
| #12mm main bar TOP & Bot | 2 | X | 6 | 50.03 |  |  | 600.36
| #12mm main bar Lap | 2 | X | 24 | 0.6 |  |  | 28.8
| #10mm Stirupps | 2 | X | 307 | 1.6 |  | 982.4
| #8mm distribution bar | 2 | X | 3 | 50.03 | 300.18
| #8mm distribution Lap bar | 2 | X | 12 | 0.4 | 9.6
PB 02 (Loading plot form)
| #16mm main bar Top&Bot | 2 | X | 18 | 7.45 |  |  |  | 268.2
| #12mm Stirupps | 2 | X | 177 | 2.23 |  |  | 789.42
| #12mm main bar | 2 | X | 177 | 1.3 |  |  | 460.2
| #12mm distribution Top | 2 | X | 33 | 5.35 |  |  | 353.1
| #12mm distribution Bot | 2 | X | 27 | 5.35 |  |  | 288.9
| #16mm channel Welding bar | 2 | X | 12 | 1.25 |  |  |  | 30
PB 01
| #12mm main bar Top&Bot | 3 | X | 6 | 15.4 |  |  | 277.2
| #12mm main bar Lap | 3 | X | 6 | 0.8 |  |  | 14.4
| #10mm Stirupps | 3 | X | 101 | 1.63 |  | 493.89
| #8mm distribution bar | 3 | X | 3 | 15.6 | 140.4
| #8mm distribution Lap | 3 | X | 3 | 0.4 | 3.6
[6 empty] | 453.78 | 1476.29 | 2812.38 | 298.2
[6 empty] | 790.26 | 2629.38 | 4790.82 | 477
3
Column upto Top Level
C1
| #16mm main bar | 12 | X | 4 | 3.6 |  |  |  | 172.8
| #12mm main bar | 12 | X | 6 | 3.6 |  |  | 259.2
| #8mm stirupps | 12 | X | 20 | 1.3 | 312
| #8mm stirupps | 12 | X | 40 | 1.04 | 499.2
| #16mm main bar | 14 | X | 4 | 4.6 |  |  |  | 257.6
| #12mm main bar | 14 | X | 6 | 4.6 |  |  | 386.4
| #8mm stirupps | 14 | X | 26 | 1.3 | 473.2
| #8mm stirupps | 14 | X | 42 | 1.04 | 611.52
C2
| #16mm main bar | 2 | X | 4 | 3.6 |  |  |  | 28.8
| #12mm main bar | 2 | X | 4 | 3.6 |  |  | 28.8
| #8mm stirupps | 2 | X | 20 | 1.06 | 42.4
| #8mm stirupps | 2 | X | 20 | 0.82 | 32.8
| #16mm main bar | 2 | X | 4 | 4.6 |  |  |  | 36.8
| #12mm main bar | 2 | X | 4 | 4.6 |  |  | 36.8
| #8mm stirupps | 2 | X | 26 | 1.3 | 67.6
| #8mm stirupps | 2 | X | 26 | 1.06 | 55.12
C3
| #16mm main bar | 2 | X | 4 | 3.6 |  |  |  | 28.8
| #12mm main bar | 2 | X | 6 | 3.6 |  |  | 43.2
| #8mm stirupps | 2 | X | 20 | 1.26 | 50.4
| #8mm stirupps | 2 | X | 40 | 1.14 | 91.2
| #16mm main bar | 2 | X | 4 | 4.6 |  |  |  | 36.8
| #12mm main bar | 2 | X | 6 | 4.6 |  |  | 55.2
| #8mm stirupps | 2 | X | 26 | 1.26 | 65.52
| #8mm stirupps | 2 | X | 42 | 1.14 | 95.76
[6 empty] | 2396.72 | 0 | 809.6 | 561.6
[6 empty] | 4068.48 | 0 | 1355.2 | 947.2
5
1.14 | GF Lintel Beam
| #20mm main bar Top&Bot | 2 | X | 6 | 63.98 |  |  |  |  | 767.76
| #20mm main bar Lap | 2 | X | 30 | 1 |  |  |  |  | 60
| #12mm main bar | 2 | X | 2 | 42.98 |  |  | 171.92
| #12mm main bar Lap | 2 | X | 10 | 0.6 |  |  | 12
| #8mm Stirupps | 2 | X | 423 | 1.38 | 1167.48
| #20mm main bar Top&Bot | 2 | X | 6 | 15.4 |  |  |  |  | 184.8
| #20mm main bar Lap | 2 | X | 6 | 1 |  |  |  |  | 12
| #12mm main bar | 2 | X | 2 | 15.4 |  |  | 61.6
| #12mm main bar Lap | 2 | X | 2 | 0.66 |  |  | 2.64
| #8mm Stirupps | 2 | X | 101 | 1.38 | 278.76
Cut Lintel beam
| #12mm main bar Top&Bot | 20 | X | 4 | 1.1 |  |  | 88
| #8mm Stirupps | 20 | X | 8 | 0.85 | 136
| #12mm main bar | 20 | X | 6 | 0.75 |  |  | 90
| #8mm distribution bar | 20 | X | 1 | 1.1 | 22
Rolling Shutter Beam
| #12mm main bar | 6 | X | 16 | 1.33 |  |  | 127.68
| #8mm distribution bar | 6 | X | 7 | 2.4 | 100.8
Open lintel
| #16mm main bar | 2 | X | 4 | 2.4 |  |  |  | 19.2
| #8mm Stirupps | 2 | X | 16 | 0.8 | 25.6
[6 empty] | 1730.64 | 0 | 553.84 | 19.2 | 1024.56
[6 empty] | 2894.16 | 0 | 1009.32 | 38.4 | 1785.12
7
1.14 | Top Tie Beam
| #20mm main bar Bot | 2 | X | 2 | 63.98 |  |  |  |  | 255.92
| #20mm main bar Lap | 2 | X | 10 | 1 |  |  |  |  | 20
| #16mm main bar Top&Bot | 2 | X | 4 | 63.98 |  |  |  | 511.84
| #16mm main bar Lap | 2 | X | 20 | 0.8 |  |  |  | 32
| #12mm main bar | 2 | X | 2 | 63.98 |  |  | 255.92
| #12mm main bar Lap | 2 | X | 10 | 0.6 |  |  | 12
| #8mm Stirupps | 2 | X | 423 | 1.37 | 1159.02
| #20mm main bar Bot | 2 | X | 2 | 15.4 |  |  |  |  | 61.6
| #20mm main bar Lap | 2 | X | 8 | 1 |  |  |  |  | 16
| #16mm main bar Top&Bot | 2 | X | 4 | 15.4 |  |  |  | 123.2
| #16mm main bar Lap | 2 | X | 4 | 0.8 |  |  |  | 6.4
| #12mm main bar | 2 | X | 2 | 15.4 |  |  | 61.6
| #12mm main bar Lap | 2 | X | 2 | 0.6 |  |  | 2.4
| #8mm Stirupps | 2 | X | 101 | 1.37 | 276.74
[6 empty] | 1435.76 | 0 | 331.92 | 673.44 | 353.52
[6 empty] | 2398.4 | 0 | 577.44 | 1172.48 | 619.04
| Total Length = |  |  |  |  | 10151.3 | 2629.38 | 7732.78 | 2635.08 | 2404.16
| Unit Wt = |  |  |  |  | 0.395 | 0.62 | 0.889 | 1.58 | 2.47
| Total Weight in Kg = |  |  |  |  | 4009.7635 | 1630.2156 | 6874.4414 | 4163.4264 | 5938.2752
| Total Weight in Qtl= |  |  |  |  | 40.0976 | 16.3022 | 68.7444 | 41.6343 | 59.3828
226.1612

## Toilet
Goundampalayam Steel - BBS RA01
S.no | Description | No's |  |  | Cutting Length | #8mm | #10mm | #12mm
[6 empty] | Wt - Kg | Wt - Kg | Wt - Kg
DAY 2
1 | Toilet
| #12mm Footing mat(both way) | 6 | X | 16 | 1.1 | 0 | 0 | 105.6
2 | Column (up to parapet wall)
| #12mm main bar | 6 | X | 4 | 5.83 | 0 | 0 | 139.92
| #8mm strriups | 6 | X | 58 | 0.65 | 226.2 | 0 | 0
[6 empty] | 226.2 | 0 | 245.52
DAY 5
1 | Septic Tank Cover Slab
| #10mm Main bar | 1 | X | 35 | 1.7 |  | 59.5
| #10mm Distributor | 1 | X | 18 | 3 |  | 54
[6 empty] | 0 | 113.5 | 0
SET10
1 | Fot Toilet plinth beam
Allround
| #12mm main bar | 1 | X | 4 | 17.72 | 0 | 0 | 70.88
| #8mm strriups | 1 | X | 177 | 0.77 | 136.29 | 0 | 0
Longitutional wall
| #12mm main bar | 1 | X | 4 | 5.2 | 0 | 0 | 20.8
| #8mm strriups | 1 | X | 52 | 0.53 | 27.56 | 0 | 0
cross wall
| #12mm main bar | 1 | X | 4 | 3.2 | 0 | 0 | 12.8
| #8mm strriups | 1 | X | 32 | 0.53 | 16.96 | 0 | 0
[6 empty] | 180.81 | 0 | 104.48
SET17
Toilet -lintel beam
Allround
| #12mm main bar | 1 | X | 4 | 17.8 | 0 | 0 | 71.2
| #8mm strriups | 1 | X | 177 | 0.61 | 107.97 | 0 | 0
Longitutional wall
| #12mm main bar | 1 | X | 4 | 5.5 | 0 | 0 | 22
| #8mm strriups | 1 | X | 55 | 0.51 | 28.05 | 0 | 0
cross wall
| #12mm main bar | 3 | X | 4 | 3.2 | 0 | 0 | 38.4
| #8mm strriups | 3 | X | 32 | 0.51 | 48.96 | 0 | 0
[6 empty] | 184.98 | 0 | 131.6
SET20
Toilet -beam
Allround
| #12mm main bar | 1 | X | 4 | 17.72 | 0 | 0 | 70.88
| #8mm strriups | 1 | X | 177 | 0.77 | 136.29 | 0 | 0
Longitutional wall
| #12mm main bar | 1 | X | 4 | 5.2 | 0 | 0 | 20.8
| #8mm strriups | 1 | X | 52 | 0.61 | 31.72 | 0 | 0
cross wall
| #12mm main bar | 3 | X | 4 | 2.13 | 0 | 0 | 25.56
| #8mm strriups | 3 | X | 21 | 0.61 | 38.43 | 0 | 0
toilet-roof
| #10mm mainbar | 1 | X | 37 | 5.56 | 0 | 205.72 | 0
| #10mm mainbar | 1 | X | 55 | 3.56 | 0 | 195.8 | 0
[6 empty] | 206.44 | 401.52 | 117.24
| Total Length = |  |  |  |  | 798.43 | 401.52 | 598.84
| Unit Wt = |  |  |  |  | 0.395 | 0.62 | 0.889
| Total Weight in Kg = |  |  |  |  | 315.3799 | 248.9424 | 532.3688
| Total Weight in Qtl= |  |  |  |  | 3.1538 | 2.4894 | 5.3237